## Mobile
| Initial Setup | Dev hrs. | QA hrs.
1 | Set up the Kick off meeting | 6
2 | Development environment setup | 4
3 | Application process flow design | 4
4 | Database design and setup | 8
5 | Nerwork reachability check | 8 | 4
Login
6 | UI design for login page | 2 | 1
7 | Integrating the api call to authenticate the user | 4 | 2
8 | parsing the api response | 4 | 2
9 | Adding validaton for email id format | 2 | 1
10 | Validation check for each required field input by the user | 2 | 1
Sign Up
11 | UI design for Sign up page | 4 | 2
12 | Integrating the api call to register a user with the details | 4 | 2
13 | parsing the api response | 4 | 2 |  | s
14 | Validation check for each required field input by the user | 4 | 2
Forgot password
15 | Integrating the api call to send the email about the system generated info to reset password | 2 | 1
16 | Forgot password logic Implemention | 6 | 3
Admin Dashboard
17 | UI design of product list | 4 | 2
18 | Integrating the api call to fetch all the products | 4 | 2
19 | Parsing the api response | 4 | 2
20 | Add/Edit individual product | 10 | 5
21 | Bulk upload of products | 12 | 6
Normal User(Physicians/nurses/pharmacists) Dashbord
22 | UI design for Dashboard page | 4 | 2
23 | Choose pharmaceutical company to fill report form | 4 | 2
24 | UI design for report form | 6 | 3
25 | Validation check for each required field input by the user | 10 | 5
26 | Ability to edit the report form informations | 6 | 2
27 | Generate and send pdf to pharmaceutical company | 16 | 8
Change Password
28 | UI design for change password page | 4 | 2
29 | Integrating the api call to update the password | 4 | 2
30 | parsing the api response | 4 | 2
31 | Validation check for each required field input by the user | 2 | 1
Deployment
32 | Deployment of the app | 24
33 | App crash testing | 16 | 10
|  | 202 | 79 | 281