## Sheet2
SalesCafe |  |  |  |  | 2013-10-28 | 2013-10-29 | 2013-10-30 | 2013-10-31 | 2013-11-01 | 2013-11-02 | 2013-11-03 | 2013-11-04 | 2013-11-05 | 2013-11-06 | 2013-11-07 | 2013-11-08 | 2013-11-09 | 2013-11-10 | 2013-11-11 | 2013-11-12 | 2013-11-13 | 2013-11-14 | 2013-11-15 | 2013-11-16 | 2013-11-17 | 2011-08-20 | 2011-08-21 | 2011-08-22 | 2011-08-23 | 2011-08-24 | 2011-08-25 | 2011-08-26 | 2011-08-27 | 2011-08-28 | 2011-08-29 | 2011-08-30 | 2011-08-31 | 2011-09-01 | 2011-09-02 | 2011-09-03 | 2011-09-04 | 2011-09-05 | 2011-09-06 | 2011-09-07 | 2011-09-08 | 2011-09-09 | 2011-09-10 | 2011-09-11 | 2011-09-12 | 2011-09-13 | 2011-09-14 | 2011-09-03 | 2011-09-04 | 2011-09-05 | 2011-09-06 | 2011-09-07 | 2011-09-08 | 2011-09-09 | 2011-09-10 | 2011-09-11 | 2011-09-12 | 2011-09-13 | 2011-09-14 | 2011-09-15
[5 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Sl# | Module | Description | Hrs. | Resource
`
User Management
|  | New User/Invite User popup design | 2 | SUM | bar: M
|  | New User creation with validation, Privilege and assign to a group | 6 | SUM | bar: M
|  | User Listing for admin with design | 4 | SUM | bar: T
|  | Source Listing with design | 4 | SUM | bar: T
|  | Industry Listing with design | 4 | SUM | bar: W
|  | Creation of new source and new industry | 8 | SUM | bar: W to T
|  | QA/Bug Fixing | 4 | SUM | bar: T
Contact
|  | Integrate the contact popup design | 4 | AMT | bar: M
|  | Create Individual contact with validation | 4 | AMT | bar: M
|  | Create Company contact with validation | 4 | AMT | bar: T
|  | Contact Listing page | 4 | AMT | bar: T
|  | Design Edit contact page | 3 | AMT | bar: W
|  | Functionality of edit contact page | 4 | AMT | bar: W
|  | QA/Bug Fixing | 4 | AMT | bar: T
Deal
|  | Integrate the contact popup design | 4 | KRS | bar: M
|  | Create new deal with validation and privelege | 6 | KRS | bar: M to T
|  | Integrate autocomelete in “FirstName” field with name and email | 6 | KRS | bar: T
|  | Integration of Source and industry in a deal | 4 | KRS | bar: W
|  | Deal assignment to a user(Default me) | 4 | KRS | bar: W
|  | Deal Privilege | 4 | KRS | bar: T
|  | Deal Listing Page | 8 | KRS | bar: T to F
|  | Design Edit Deal page | 3 | KRS | bar: F
|  | Functionality of edit Deal page | 4 | KRS | bar: F; M
|  | QA/Bug Fixing | 6 | KRS | bar: M
Task
|  | Integrate the Task popup design | 4
|  | Task creation | 6
|  | Task assignment to a user | 2
|  | Task Assignment to a Deal | 2 | bar: M to W
|  | Task Listing Page Grid view | 6 | bar: M to W
|  | Task Listing Page Calendar view | 8 | bar: M to F; M to F
|  | QA/Bug Fixing | 6 | bar: M to F
Dashboard
Report
Activity
Social Feed
| Profile | Edit Profile
Change Password
Search functionality
Notification
|  | Total | 142 | bar: M to F; M to F; M to F
Developer
QA

## Sheet1 (hidden)
Sl# | Section | Description | Hrs.
User
1 |  | Showing submenu upon mousehover Login button with Link named Customer, Support Area | 6
2 |  | Creating common login page for Customer & Support area | 4
2 |  | Designing Support Area page | 6
3 |  | Showing file list in Support Area | 8
4 |  | Link availability calculation page | 12
5 |  | Fresnel Zone calculation page | 24
6 |  | GPS bearing and distance calculation page | 8
7 |  | Adding new Flash into home page | 3
8 |  | Allow selection of either the ANSI or the ETSI version | 8
Admin
1 |  | Designing Support Area manipulation page | 4
2 |  | Creating Support Area page for Customer with temporary password creation | 10
3 |  | Functionality of adding files to individual customer | 10
4 |  | File list view page for Customer in support area | 6
|  | Designing slide flash for six products | 16
|  | Writing test cases | 20
|  | QA | 32
|  | Total | 177
* |  | Mock up of Flash and creation will be taken care by Bijoy