## API
Estimation for Trophy Cocktail API
# | Item | Dev hr | QA hr
Trophy Cocktails
5 | Save the new post information to the database | 8
6 | Send the bartender informations like images, name based on the entered bar name & location, while creating the post | 4
7 | Send the particular post information for display purpose | 4
8 | Save the comments for the post | 4
9 | Update the like count for the post | 4
Recipe
10 | Send the recipe information of the requested post | 2
Bartender
11 | Save the bartender information to the database | 4
12 | Send the bartender information for the profile page | 4
13 | Send the bartender informations like images, name based on the entered bar name & location, while creating the post | 4
Comments
14 | Send all the comments of the requested post | 2
15 | Save the new comment added | 2
Ads
16 | Send the Splash Screen information as per the settings from the admin panel | 2
News Flash
17 | Send the news flash information as per the settings from the admin panel | 2
18 | Update the vote/point for the user as a response | 2
Brain Tease
19 | Send the Brain Tease information as per the settings from the admin panel | 2
20 | Update the vote/point for the user as a response | 2
Treasure Hunt
21 | Send the Treasure Hunt information as per the settings from the admin panel | 2
22 | Update the vote/point & limit on participation for the user | 2
Cocktail of the Day
23 | Send the Cocktail of the Day post with the postion 3 | 3
Registration
Registration Form
24 | Send the Terms & Conditions and Privacy Policy (optional) | 2
25 | Send the city, Spirits & Role information | 4
26 | Save the user registration information (with facebook also) | 8
27 | Save the facebook profile image if registered through facebook | 4
Select Favorite Spirits
28 | Send all the list of spirits | 2
Select Role
29 | Send all the Role information | 2
Bartender, Bar Manager or Bar Owner is selected
30 | Save the bar information if the role selected is Bartender, Bar Manager or Bar Owner | 4
31 | Save the added images | 6
Media/PR is selected
32 | Save the all the detail information | 2
Brand Ambassador or Sales/Marketing, Production is selected
33 | Save the newly registered spirit information(Brand input) | 3
34 | Save all the detail information | 2
Other
35 | Save all the detail information | 2
Tailor Your Feed
36 | Save the selected facebook friends information on invite | 6
37 | Update the friends list as per the add/remove functionalty | 2
38 | Send the list of expert users | 2
39 | Send the users from the nearby cities as per the user's location | 8
40 | Send the search result for the people located within the app | 4
Login
41 | Send the user information & user token to validate the login (also with the FB) | 8
Profiles
42 | Send the user profile information as per the user role | 6
43 | Update the user information on follow or unfollow | 2
44 | Update the user information on update user | 2
View Friends or Add Friends
45 | Send the list of all the users they are following | 2
Camera
46 | Saved the uploaded photo | 2
Bar Selection
47 | Send the search result for the bar information | 4
48 | Save the bar information | 2
Drink Name Selection
49 | Send the cocktail list for suggestion | 4
50 | Save the cocktail information | 2
Bartender Selection
51 | Send the bartender list as a search result | 2
Recipe
52 | Send the brand name & category list as a search result | 2
53 | Save the brand name for the selected sprit (max 5 for an user) | 4
Flavor Profile
54 | Send the flavor profile names with category | 2
Social sharing
55 | To share the post in the social networks
Trending
What’s Hot
56 | Send the latest 50 post information (3 to 4 per page) | 6
Best Bars
57 | Send the best bars as per time based & location based | 8
Experts
58 | Send the result for advance search | 8
Brand Page
59 | Send the brand information | 2
60 | Send the search result for the brand | 4
61 | Send email notification month basis for the upgraded brand page | 6

## Admin Interface
Estimation for Trophy Cocktail Web Admin
# | Item | Dev hr | QA hr
Initial Setup
1 | Development environment setup | 8
2 | Database architecture design | 8
3 | Application process flow design | 16
4 | UI design build | 24
| Implement Authentication system | 4
Ad Management
Splash Screen or Interstitial Ads
| Create/Edit form page design | 4
| Implement to save the information | 4
| Ad preview page | 2
| Display the form page to schedule a ads | 4
| Implement the functionality to schedule the ads | 4
| Implement to export as CSV file by sponsors and campaigns | 8
News Flash
| Create/Edit form page design | 4
| Implement to save the information | 4
| Ad preview page | 2
| Display the form page to schedule a ads | 4
| Implement the functionality to schedule the ads | 4
| Implement to export as CSV file by sponsors and campaigns | 8
Brain Tease
| Create/Edit form page design | 4
| Ad preview page | 2
| Implement the functionality to save two response questions & answers for the small size ad | 2
| Implement the functionality to save 4 response questions & answers for the medium or large size ads | 6
| Implement the functionality to save poll information for the medium or large size ads | 4
| Form page to schedule ads | 2
| Implement the functionality to schedule the ads | 2
| Implement to export as CSV file by sponsors and campaigns | 4
Treasure Hunt
| Create/Edit form page design | 4
| Implement to save the information for 3 sizes of ads | 4
| Display the form page to schedule a ads | 4
| Implement the functionality to schedule the ads | 4
| Send email notification for the awarded points | 4
| Implement to export as CSV file by sponsors and campaigns | 8
Cocktail Of The Day
| Implement the functionality to make a post "Cocktail of the day" | 2
| Create a Trophy lab profile page | 2
| Implement the functionality to to display the post up to 24 hours | 2
| Implement the functionality to add posts to the queue if more than one post is selected | 4
User Management
| Registered user listing page | 4
| User edit/delete functionality | 2
| User search functionality | 4
| User detail page with other information | 3
| Implement export CSV file with all the users | 8
Brand Page Management
| Create Brand Pages form | 2
| Implement the functionality to save the brand page information | 4
| Implement the functionality to manage brand page | 2
Reporting
| Total number of app users | 4
| Registration over time | 8
| Usage (or time spent on app) over time | 8
| Number of posts over time | 8
| Activity by region or city | 4
| Activity by user group | 4
| Inactive users over time | 4
| Visits per Brand page over time | 4
| Visits per Bartender page over time | 4
| Posts with the most “Likes” and/or “Comments” | 4
| Users who post the most | 4
| Listing of Bars by number of posts | 4
| Listing of Bartenders by number of posts | 4
| Crash and Exception Reporting | 4
| Event Tracking | 8
| Traffic Sources | 8
| Ad Viewing and Click Through | 8
| Export CSV files and allow for individual reporting for sponsor | 16