## Phase II
Salk Metabolic Phase-II | [5 empty] | 2014-09-22 | 2014-09-23 | 2014-09-24 | 2014-09-25 | 2014-09-26 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-10-10 | 2014-10-11 | 2014-10-12 | 2014-10-13 | 2014-10-14 | 2014-10-15 | 2014-10-16 | 2014-10-17 | 2014-10-18
[6 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Type | Module | Description | Status | Hrs. | Resource
WEB | bar: 2014-09-25
Coordinator
|  | Store Organization information of coordinator | Done | 2 | SUM | bar: 2014-09-22
|  | Auto populate address from the organization | Done | 2 | SUM | bar: 2014-09-22
|  | First time need to enter the detail of the organization | Done | 1 | SUM | bar: 2014-09-22
|  | Add Question category i.e screening, 1st visit, 2nd visit ..etc | Done | 6 | SUM | bar: 2014-09-22 to 2014-09-23
|  | Add/Edit/Delete Question for category wise | Done | 8 | SUM | bar: 2014-09-23 to 2014-09-24
|  | While adding a question need to select the terms and condition that following the IRB(not required) | ABRT | 2 | SUM | bar: 2014-09-24
|  | Validation to restrict rejected participant signup for same research study | Done | 2 | SUM | bar: 2014-09-24
|  | Add new button "Schedule meeting" & "Reject" functionality and remove the "Approve" button form the participant listing page | Done | 4 | SUM | bar: 2014-09-24
|  | Appointment schedule email will be sent to the participant | Done | 2 | SUM | bar: 2014-09-24
|  | Add "Today's appointments" menu | Done | 0.5 | SUM | bar: 2014-09-24
|  | On clicking the button, participant list will be displayed | Done | 2 | SUM | bar: 2014-09-24 to 2014-09-25
|  | Add "Clinical investigation" button | Done | 0.5 | SUM | bar: 2014-09-25
|  | On clicking, form to enter investigation report of each participant will appear | Done | 1.5 | SUM | bar: 2014-09-25
|  | Auto suggest on adding email | Done | 1 | SUM | bar: 2014-09-25
|  | On submitting the report, the participant will be activated and the access code will be generated | Done | 2 | SUM | bar: 2014-09-25
|  | Investigation detail page of participant | Done | 1 | SUM | bar: 2014-09-25
|  | Tab to display the record of each visit | Done | 2 | SUM | bar: 2014-09-25 to 2014-09-26
|  | Add/Edit/Delete of investigation report | Done | 2 | SUM | bar: 2014-09-26
|  | Save the weekdays and weekend information of each participant | ABRT | 1.5 | SUM | bar: 2014-09-26
|  | Set timer for recording weights | ABRT | 1 | SUM | bar: 2014-09-26
|  | Set timers for recording blood sugar or any other parameter the participant is supposed to measure at regular interval | ABRT | 1 | SUM | bar: 2014-09-26; 2014-09-29
|  | Set timer for taking medications | ABRT | 1 | SUM | bar: 2014-09-29
|  | Push notification functionality |  | 2 | SUM | bar: 2014-09-29
|  | Send the push notification to the participant as per the set timings |  | 1 | SUM | bar: 2014-09-29
|  | CRUD for encouraging notes | Done | 1 | SUM | bar: 2014-09-29
|  | Send the encouraging notes for completing - day 1, day 2, day 3, day 7, 2 weeks. |  | 2 | SUM | bar: 2014-09-29 to 2014-09-30
|  | Push notification to measure the false positive and false negative rates |  | 1.5 | SUM | bar: 2014-09-30
|  | Functionality to measure the false positive and false negative rates and save againt the participant |  | 2 | SUM | bar: 2014-09-30
|  | Depending upon the last day activity notification will be sent |  | 2 | SUM | bar: 2014-09-30; 2014-10-06
|  | Only 10 push notification will be allowed for each participant |  | 1 | SUM | bar: 2014-10-06
| Participant | On participant signup, an email will be sent to the participant which will say that your application is pending for review by coordinator | Done | 1 | SUM | bar: 2014-10-06
|  | Send group of participant email to the coordinator once a day | Done | 3 | SUM | bar: 2014-10-06
|  | On approve, approval email will be sent with the access code, next lab visit date and the link to download the app | Done | 2 | SUM | bar: 2014-10-06 to 2014-10-07
|  | On Reject, rejection email will be sent | Done | 1 | SUM | bar: 2014-10-07
|  | Drop out functionality, where study coordinator can disqualify a participant in between the research process like inactive | Done | 4 | SUM | bar: 2014-10-07
|  | Notify the coordinator if any participant is not active for some period (add a cron job, which will check the activity of all the participant, if a participant is not active for like 2days(set by admin), then notification email will be sent to the coordinator) | Done | 3 | SUM | bar: 2014-10-07 to 2014-10-08
|  | Enable/Disable option for notification | Done | 2 | SUM | bar: 2014-10-08
|  | Add option to disable account(if mobile has stolen) | Done | 2 | SUM | bar: 2014-10-08
|  | Generate Feedogram with the filter option | Done | 4 | SUM | bar: 2014-10-08 to 2014-10-09
|  | Generate the percentage chart and cumulative report | Done | 3 | SUM | bar: 2014-10-09
|  | Calculate hours of fasting, eating and jetlag |  | 3 | SUM | bar: 2014-10-09 to 2014-10-10
| Landing Page | Engine to create ad having the validity date | Done | 3 | SUM | bar: 2014-10-10
|  | Display of the ad related to research study on the landing page |  | 2 | SUM | bar: 2014-10-10; 2014-10-13
|  | On clicking the ad, it will redirect the user to the participant sign up page | Done | 2 | SUM | bar: 2014-10-13
|  | Where the research will be selected and the questions will be displayed | Done | 2 | SUM | bar: 2014-10-13
| Sign Up | There will be a captcha either a question or image | Done | 2 | SUM | bar: 2014-10-13 to 2014-10-14
API |  | Send appointment schedule while activating the participant | Done | 2 | SUM | bar: 2014-10-14
|  | Save the image, annotation and time information | Done | 3 | SUM | bar: 2014-10-14
|  | Send common food list in asc order of most frequently used | Done | 2 | SUM | bar: 2014-10-14
Mobile |  | Fetching the appointment information from the server and update the device calender and app calendar | Done | 4 | MRM | bar: 2014-09-22
|  | Add menu to view calendar |  | 4 | MRM | bar: 2014-09-22
|  | Alert participant regarding the appointment |  | 2 | MRM | bar: 2014-09-23
|  | On opening the app, call the API to authenticate the participant |  | 2 | MRM | bar: 2014-09-23
|  | New tabs to "take picture" or to select "common foods" |  | 4 | MRM | bar: 2014-09-24
| Take picture | Implementing the camera feature (square image) |  | 4 | MRM | bar: 2014-09-24
|  | Resizing the image option (image should be < 300KB) |  | 16 | MRM | bar: 2014-09-25 to 2014-09-26
|  | Saving the picture in the local storage |  | 8 | MRM | bar: 2014-09-29
|  | Displaying the image in a view with functionality to add annotation(auto complete) and timing(timepicker with after/before) |  | 8 | MRM | bar: 2014-09-30
|  |  |  | 8 | MRM | bar: 2014-10-06
|  | Display 4 bins like food, beverage, water & medication |  | 8 | MRM | bar: 2014-10-07
|  | Drag & Drop functionality to add the image to the bin |  | 8 | MRM | bar: 2014-10-08
|  | Send button to send the data |  | 8 | MRM | bar: 2014-10-09
|  | Verify the internet connection. if exist then call the API, else store in the local db |  | 4 | MRM | bar: 2014-10-10
|  | Check the internet at regular interval, and send the data if exist |  | 4 | MRM | bar: 2014-10-10
| Common Foods | Display the common food from local database with image in a list view (Maintain the count of repeated used food, it will be used to display in asc order and add indexing) |  | 6 | MRM | bar: 2014-10-13
|  | Clicking on the common food, display alert message with time picker and before/after wheel |  | 6 | MRM | bar: 2014-10-13 to 2014-10-14
|  | Display 4 bins like food, beverage, water & medication |  | 6 | MRM | bar: 2014-10-14 to 2014-10-15
|  | Drag & Drop functionality to add the image to the bin |  | 6 | MRM | bar: 2014-10-15
|  | Verify the internet connection. if exist then call the API, else store in the local db |  | 4 | MRM | bar: 2014-10-16
|  | Total |  | 69.5 | bar: 2014-10-15 to 2014-10-18
Developer
QA
Remaining Task iOS
| Common food | Checking network reachabilty before sending common foods to web
storing files in local db if no internet
sending file when internet is back
| Manual entry | Checking network reachabilty before sending foods
storing files in local db if no internet
sending file when internet is back
Write data to file
| Image entry | Checking network reachabilty before sending images
storing files in local db if no internet
sending file when internet is back

## Android
Module | Description | Status | Hrs. | Resource
Authenticate
| Fetching the appointment information from the server and update the device calender and app calendar |  |  | SRS
| Add menu to view calendar |  |  | SRS
| Alert participant regarding the appointment |  |  | SRS
| On opening the app, call the API to authenticate the participant |  |  | SRS
Take picture
| New tabs to "take picture" or to select "common foods" |  |  | SRS
| Implementing the camera feature (square image) |  |  | SRS
| Resizing the image option (image should be < 300KB) |  |  | SRS
| Saving the picture in the local storage |  |  | SRS
| Displaying the image in a view with functionality to add annotation(auto complete) and timing(timepicker with after/before) |  |  | SRS
| Display 4 bins like food, beverage, water & medication |  |  | SRS
| Drag & Drop functionality to add the image to the bin |  |  | SRS
| Send button to send the data |  |  | SRS
| Verify the internet connection. if exist then call the API, else store in the local db |  |  | SRS
| Check the internet at regular interval, and send the data if exist |  |  | SRS
Common Foods
| Display the common food from local database with image in a list view (Maintain the count of repeated used food, it will be used to display in asc order and add indexing) |  |  | UTM
| Clicking on the common food, display alert message with time picker and before/after wheel |  |  | UTM
| Display 4 bins like food, beverage, water & medication |  |  | UTM
| Drag & Drop functionality to add the image to the bin |  |  | UTM
| Verify the internet connection. if exist then call the API, else store in the local db |  |  | UTM

## Phase III
Salk Metabolic Phase-III |  |  |  |  | 2014-09-22 | 2014-09-23 | 2014-09-24 | 2014-09-25 | 2014-09-26 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-10-10 | 2014-10-11 | 2014-10-12 | 2014-10-13 | 2014-10-14 | 2014-10-15 | 2014-10-16 | 2014-10-17 | 2014-10-18
[5 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Type | Module | Description | Hrs. | Resource
WEB | bar: 2014-09-25
Coordinator
|  | Store Organization information of coordinator | 2 | SUM | bar: 2014-09-22
|  | Auto populate address from the organization | 2 | SUM | bar: 2014-09-22
|  | First time need to enter the detail of the organization | 1 | SUM | bar: 2014-09-22
|  | Add Question category i.e screening, 1st visit, 2nd visit ..etc | 4 | SUM | bar: 2014-09-22 to 2014-09-23
|  | Add/Edit/Delete Question for category wise | 4 | SUM | bar: 2014-09-23
|  | While adding a question need to select the terms and condition that following the IRB(not required) | 2 | SUM | bar: 2014-09-23 to 2014-09-24
|  | Validation to restrict rejected participant signup for same research study | 2 | SUM | bar: 2014-09-24
|  | Add new button "Schedule meeting" & "Reject" functionality and remove the "Approve" button form the participant listing page | 2 | SUM | bar: 2014-09-24
|  | Appointment schedule email will be sent to the participant | 1 | SUM | bar: 2014-09-24
|  | Add "Today's appointments" menu | 0.5 | SUM | bar: 2014-09-24
|  | On clicking the button, participant list will be displayed | 1.5 | SUM | bar: 2014-09-24 to 2014-09-25
|  | Add "Clinical investigation" button | 0.5 | SUM | bar: 2014-09-25
|  | On clicking, form to enter investigation report of each participant will appear | 1.5 | SUM | bar: 2014-09-25
|  | Auto suggest on adding email | 1 | SUM | bar: 2014-09-25
|  | On submitting the report, the participant will be activated and the access code will be generated | 2 | SUM | bar: 2014-09-25
|  | Investigation detail page of participant | 1 | SUM | bar: 2014-09-25
|  | Tab to display the record of each visit | 2 | SUM | bar: 2014-09-25 to 2014-09-26
|  | Add/Edit/Delete of investigation report | 2 | SUM | bar: 2014-09-26
|  | Save the weekdays and weekend information of each participant | 1.5 | SUM | bar: 2014-09-26
|  | Set timer for recording weights | 1 | SUM | bar: 2014-09-26
|  | Set timers for recording blood sugar or any other parameter the participant is supposed to measure at regular interval | 1 | SUM | bar: 2014-09-26; 2014-09-29
|  | Set timer for taking medications | 1 | SUM | bar: 2014-09-29
|  | Push notification functionality | 2 | SUM | bar: 2014-09-29
|  | Send the push notification to the participant as per the set timings | 1 | SUM | bar: 2014-09-29
|  | CRUD for encouraging notes | 1 | SUM | bar: 2014-09-29
|  | Send the encouraging notes for completing - day 1, day 2, day 3, day 7, 2 weeks. | 2 | SUM | bar: 2014-09-29 to 2014-09-30
|  | Push notification to measure the false positive and false negative rates | 1.5 | SUM | bar: 2014-09-30
|  | Functionality to measure the false positive and false negative rates and save againt the participant | 2 | SUM | bar: 2014-09-30
|  | Depending upon the last day activity notification will be sent | 2 | SUM | bar: 2014-09-30; 2014-10-06
|  | Only 10 push notification will be allowed for each participant | 1 | SUM | bar: 2014-10-06
| Participant | On participant signup, an email will be sent to the participant which will say that your application is pending for review by coordinator | 1 | SUM | bar: 2014-10-06
|  | Send group of participant email to the coordinator once a day | 3 | SUM | bar: 2014-10-06
|  | On approve, approval email will be sent with the access code, next lab visit date and the link to download the app | 2 | SUM | bar: 2014-10-06 to 2014-10-07
|  | On Reject, rejection email will be sent | 1 | SUM | bar: 2014-10-07
|  | Drop out functionality, where study coordinator can disqualify a participant in between the research process like inactive | 4 | SUM | bar: 2014-10-07
|  | Notify the coordinator if any participant is not active for some period (add a cron job, which will check the activity of all the participant, if a participant is not active for like 2days(set by admin), then notification email will be sent to the coordinator) | 3 | SUM | bar: 2014-10-07 to 2014-10-08
|  | Enable/Disable option for notification | 2 | SUM | bar: 2014-10-08
|  | Add option to disable account(if mobile has stolen) | 2 | SUM | bar: 2014-10-08
|  | Generate Feedogram with the filter option | 4 | SUM | bar: 2014-10-08 to 2014-10-09
|  | Generate the percentage chart and cumulative report | 3 | SUM | bar: 2014-10-09
|  | Calculate hours of fasting, eating and jetlag | 3 | SUM | bar: 2014-10-09 to 2014-10-10
| Landing Page | Engine to create ad having the validity date | 3 | SUM | bar: 2014-10-10
|  | Display of the ad related to research study on the landing page | 2 | SUM | bar: 2014-10-10; 2014-10-13
|  | On clicking the ad, it will redirect the user to the participant sign up page | 2 | SUM | bar: 2014-10-13
|  | Where the research will be selected and the questions will be displayed | 2 | SUM | bar: 2014-10-13
| Sign Up | There will be a captcha either a question or image | 2 | SUM | bar: 2014-10-13 to 2014-10-14
API |  | Send appointment schedule while activating the participant | 2 | SUM | bar: 2014-10-14
|  | Save the image, annotation and time information | 3 | SUM | bar: 2014-10-14
|  | Send common food list in asc order of most frequently used | 2 | SUM | bar: 2014-10-14
Mobile |  | Fetching the appointment information from the server and update the device calender and app calendar | 4 | MRM | bar: 2014-09-22
|  | Add menu to view calendar | 4 | MRM | bar: 2014-09-22
|  | Alert participant regarding the appointment | 2 | MRM | bar: 2014-09-23
|  | On opening the app, call the API to authenticate the participant | 2 | MRM | bar: 2014-09-23
|  | New tabs to "take picture" or to select "common foods" | 4 | MRM | bar: 2014-09-24
| Take picture | Implementing the camera feature (square image) | 4 | MRM | bar: 2014-09-24
|  | Resizing the image option (image should be < 300KB) | 16 | MRM | bar: 2014-09-25 to 2014-09-26
|  | Saving the picture in the local storage | 8 | MRM | bar: 2014-09-29
|  | Displaying the image in a view with functionality to add annotation(auto complete) and timing(timepicker with after/before) | 8 | MRM | bar: 2014-09-30
|  |  | 8 | MRM | bar: 2014-10-06
|  | Display 4 bins like food, beverage, water & medication | 8 | MRM | bar: 2014-10-07
|  | Drag & Drop functionality to add the image to the bin | 8 | MRM | bar: 2014-10-08
|  | Send button to send the data | 8 | MRM | bar: 2014-10-09
|  | Verify the internet connection. if exist then call the API, else store in the local db | 4 | MRM | bar: 2014-10-10
|  | Check the internet at regular interval, and send the data if exist | 4 | MRM | bar: 2014-10-10
| Common Foods | Display the common food from local database with image in a list view (Maintain the count of repeated used food, it will be used to display in asc order and add indexing) | 6 | MRM | bar: 2014-10-13
|  | Clicking on the common food, display alert message with time picker and before/after wheel | 6 | MRM | bar: 2014-10-13 to 2014-10-14
|  | Display 4 bins like food, beverage, water & medication | 6 | MRM | bar: 2014-10-14 to 2014-10-15
|  | Drag & Drop functionality to add the image to the bin | 6 | MRM | bar: 2014-10-15
|  | Verify the internet connection. if exist then call the API, else store in the local db | 4 | MRM | bar: 2014-10-16
|  | Total | 60 | bar: 2014-10-15 to 2014-10-18
Developer
QA

## Sheet1 (hidden)
Sl# | Section | Description | Hrs.
User
1 |  | Showing submenu upon mousehover Login button with Link named Customer, Support Area | 6
2 |  | Creating common login page for Customer & Support area | 4
2 |  | Designing Support Area page | 6
3 |  | Showing file list in Support Area | 8
4 |  | Link availability calculation page | 12
5 |  | Fresnel Zone calculation page | 24
6 |  | GPS bearing and distance calculation page | 8
7 |  | Adding new Flash into home page | 3
8 |  | Allow selection of either the ANSI or the ETSI version | 8
Admin
1 |  | Designing Support Area manipulation page | 4
2 |  | Creating Support Area page for Customer with temporary password creation | 10
3 |  | Functionality of adding files to individual customer | 10
4 |  | File list view page for Customer in support area | 6
|  | Designing slide flash for six products | 16
|  | Writing test cases | 20
|  | QA | 32
|  | Total | 177
* |  | Mock up of Flash and creation will be taken care by Bijoy