## Phase II
Salk Metabolic Phase-III and bug fixing
Type | Description | Status | Hrs. | Resource |  | Staging | Remark | QA
WEB | CSV and Excel download of participant with checkbox to select the column | CMPL | 6 | ANM | 2014-12-04 | 2014-12-09 | Done | Done
| Multiple participant apply and participant history after dropout and reject | WIP | 4 | KRS | 2014-12-04 | 2014-12-09 | To be discussed
| Daily Report (follow the page no 7 >> 2.Daily report to the coordinator) https://docs.google.com/a/andolasoft.co.in/document/d/1albWp9N9kQqPsFmke7MwjUY0MvJFxfHHe1MNMOHfD5c/edit | WIP | 5 | KRS | 2014-12-10 | 2014-12-16
| Weekly report DEFAULT: Every Monday morning for the user’s local time (4am Monday) calculate the change in breakfast time during the weekend Calculate the change in dinner (last caloric intake) during the weekend | WIP | 3 | ANM | 2014-12-09 | 2014-12-11
| Push notification >> eating time notification The time when the user answers the message is “time stamped” and sent back to the server. | CMPL | 3 | ANM | 2014-12-05 | 2014-12-11 |  | Done
| Annotation text edit >> speling correction while editing and validation for duplicate entry | CMPL | 4 | ANM | 2014-12-10 | 2014-12-11 | Issue in Firefox | Done
| Tag cloud or wordle >> new tab in the participant detail page >> display the tag cloud view of the annotation | CMPL | 5 | SUM | 2014-12-08 | 2014-12-16 |  | Done
| Time since last non-water meal >> participant detail page >> top section >> (we are storing the food_type = "f" or "b") | CMPL | 2 | ANM | 2014-12-08 | 2014-12-16 |  | Done
| food log >> Image delete button placement and zoom button for bigger view | CMPL | 1 | ANM | 2014-12-08 | 2014-12-16 |  | Done
| Dashboard for the system administrator | TBD | 6 | ANM | 2014-12-09 | 2014-12-18
| Question >> ability to add multiple option type in a question https://docs.google.com/a/andolasoft.co.in/document/d/12f2rK3-yJvyh6Qn93Xrj-H6FpZOOI5GJ3KGkmeu69w8/edit |  | 8 | KRS | 2014-12-09 | 2014-12-18
| Activity log | WIP | 8 | KRS | 2014-12-11 | 2014-12-18
| Landing Page (Need changes as per the new clinical flow chart documentation) | ABRT
API | API to send the meeting information | CMPL | 3 | ANM | 2014-12-10 | 2014-12-09 |  | Done
| Annotation will be optional Either image or annotation is mandatory with location Need to change the existing functionality as per that It will not display anything but | TBD | 6 | ANM | 2014-12-11 | 2014-12-18
.
| Total |  | 32

## Sheet1 (hidden)
Sl# | Section | Description | Hrs.
User
1 |  | Showing submenu upon mousehover Login button with Link named Customer, Support Area | 6
2 |  | Creating common login page for Customer & Support area | 4
2 |  | Designing Support Area page | 6
3 |  | Showing file list in Support Area | 8
4 |  | Link availability calculation page | 12
5 |  | Fresnel Zone calculation page | 24
6 |  | GPS bearing and distance calculation page | 8
7 |  | Adding new Flash into home page | 3
8 |  | Allow selection of either the ANSI or the ETSI version | 8
Admin
1 |  | Designing Support Area manipulation page | 4
2 |  | Creating Support Area page for Customer with temporary password creation | 10
3 |  | Functionality of adding files to individual customer | 10
4 |  | File list view page for Customer in support area | 6
|  | Designing slide flash for six products | 16
|  | Writing test cases | 20
|  | QA | 32
|  | Total | 177
* |  | Mock up of Flash and creation will be taken care by Bijoy