## PHASE(1)
Salk Metabolic Phase#1 development
# | Item | Comments
iOS Development
Initial Setup
1 | Project Kick-off meeting
2 | Development environment setup
3 | Internal storage database design
4 | UI build & integration for the iPhone app
App activation & User eligibility
5 | Activating the app through a study code through API/Webservice
6 | App summary screen after launching the app for the first time
7 | Displaying of study details & co-ordinator contact details through API/Webservice
8 | Getting the device token
9 | Sending the device token to the server through API/Webservice
10 | Creating of 20 character alphanumeric identifier for the device
11 | Sending the device identifier to server through API/Webservice
12 | Basic questionnaire screen
13 | Calculating the eligibility of the user
14 | Sending the answers along with the eligibility to the Server through API/Webservice
15 | Generating build for review & bug fixes
16 | App Build generation & Deployment of the app to the Apple app store by getting all the required information
17 | App crash testing
Android Development
Initial Setup
1 | Development environment setup
2 | Internal storage database design
3 | UI build & integration for the Android app
App activation & User eligibility
4 | Activating the app through a study code through API/Webservice
5 | App summary screen after launching the app for the first time
6 | Displaying of study details & co-ordinator contact details through API/Webservice
7 | Getting the device token
8 | Sending the device token to the server through API/Webservice
9 | Creating of 20 character alphanumeric identifier for the device
10 | Sending the device identifier to server through API/Webservice
11 | Basic questionnaire screen
12 | Calculating the eligibility of the user
13 | Sending the answers along with the eligibility to the Server through API/Webservice
14 | Generating build for review & bug fixes
16 | App Build generation & Deployment of the app to theGoogle play store by getting all the required information
17 | App crash testing
API Development
Initial Setup
1 | Development environment setup
2 | Database design/Modification
3 | Production environment setup with HIPPA compliance
Multi User login
4 | Activating the app through a study code
5 | Displaying of study details & co-ordinator contact details
6 | Saving the device token in the server
7 | Saving the device identifier in the server
8 | Updating the answers along with the eligibility in the Server
9 | Adding audit log capabilities
10 | Deployment to production server
Web Development
Initial Setup
1 | Project Kick-off meeting
2 | Development environment setup
3 | Database & Model architecture design
4 | UI build with bootstrap layout
Authentication & Study co-ordinator
5 | One time Admin user setup
6 | Authentication/Forget password/Change password
7 | Creating of Study co-ordinators/Sign up for Co-ordinator
8 | Dashboard for the study co-ordinators
9 | Dashboard for the user
10 | Assigning a unique study code to each co-ordinator
11 | Adding audit log capabilities
12 | Deployment to production server

## PHASE(2)
Salk Metabolic Phase#2 development
# | Item | Comments
iOS Development
Notification & Calendar sync
1 | Calendar showing next visit to the office/lab through API/Webservice
2 | Receiving Push notification on the food alert from server
3 | Responding to the push notification
4 | Sending user answer to the server through API/Webservice
5 | Receiving push notification on encouraging notes
Study questionire
6 | Getting device lat/long and sending to server through API/Webservice
7 | Camera functionality to take picture or select from Album
8 | Adding text annotation for the captured/selected image
9 | Sending image with text to the server through API/Webservice
10 | Saving the food names in device database to use for auto suggest next time
11 | Adding spelling correction/suggestion while entering the text annotation
12 | Adding text option functionality to allow user to input food names with an entry field for time
13 | Populating common foods with image
14 | Adding pre-defined food image/medication and scheduled time to remind
15 | Generating unique identifier for the image/text file with respect to individual user
16 | Enhancement of the image so that the size of an image reduced to <300KB
17 | Sending all the information to server through API/Webservice
18 | Generating build for review & bug fixes
19 | App Build generation & Deployment of the app to the Apple app store by getting all the required information
20 | App crash testing
Android Development
Notification & Calendar sync
1 | Calendar showing next visit to the office/lab through API/Webservice
2 | Receiving Push notification on the food alert from server
3 | Responding to the push notification
4 | Sending user answer to the server through API/Webservice
5 | Receiving push notification on encouraging notes
Study questionire
6 | Getting device lat/long and sending to server through API/Webservice
7 | Camera functionality to take picture or select from Album
8 | Adding text annotation for the captured/selected image
9 | Sending image with text to the server through API/Webservice
10 | Saving the food names in device database to use for auto suggest next time
11 | Adding spelling correction/suggestion while entering the text annotation
12 | Adding text option functionality to allow user to input food names with an entry field for time
13 | Populating common foods with image
14 | Adding pre-defined food image/medication and scheduled time to remind
15 | Generating unique identifier for the image/text file with respect to individual user
16 | Sending all the information to server through API/Webservice
17 | Enhancement of the image so that the size of an image reduced to <300KB
18 | Generating build for review & bug fixes
19 | App Build generation & Deployment of the app to theGoogle play store by getting all the required information
20 | App crash testing
API Development
1 | Getting calendar info for next visit
2 | Updating the answers responded by the user
3 | Signup
4 | authentication
5 | Forgot access code
6 | Change password
7 | Saving device location
8 | Saving image with text in server
9 | Saving information of the image, text and file in the server (Auto Sync)
10 | Getting feedogram reports
11 | Adding audit log capabilities
12 | Deployment to production
Web Development
Eligible user & Notification send
1 | Listing of all eligible subjects
2 | Sending push notification to the eligible candidates for the office visit |  | Text communication, and it will be recorded on the server
3 | Recording data of the eligible users
4 | Calendar schedule of eligible users for next office/lab visits
5 | Daily background Scheduler - Sending push notification to user regarding the food take in user specific timezone
6 | Sending encouraging notes to devices as push notification
7 | Sending push notification with respect to user activity
8 | Daily background Scheduler - Making an user inactive based on conditions
9 | Daily background Scheduler - Functionality to send inactive reminders
Questionnire management
10 | Questionnaire management
11 | Sending push notification to device for the Questionnaire set
12 | Updating database with respect to user after response from the user for the Questionnaire
13 | Dashboard for the system administrator
14 | Adding audit log capabilities
15 | Deployment to production server

## PHASE(3)
Salk Metabolic Phase#3 development
# | Item | Comments
iOS Development
Signup & Authentication
1 | Signup through mobile device for web portal using API/Webservice
2 | Authentication using API/Webservice
3 | Change password
4 | Forgot access code
Study questionire & Reports
5 | Barcode reader integration
6 | Populating the fields after barcode scan
7 | Generating unique identifier for the image/text file with respect to individual user
8 | Saving the information into device storage if internet connection is not available
9 | Sending all the information to server through API/Webservice
10 | Syncing with server through API/Webservice if any information is saved in the temp storage of the device
11 | Displaying of feedogram after certain days of research starts through API/Webservice
12 | Prompting user for the baseline period ending
13 | Set my foodzone
14 | Generating build for review & bug fixes
15 | App Build generation & Deployment of the app to the Apple app store by getting all the required information
16 | App crash testing
Android Development
Signup & Authentication
1 | Signup through mobile device for web portal using API/Webservice
2 | Authentication using API/Webservice
3 | Change password
4 | Forgot password
Study questionire & Reports
5 | Barcode reader integration
6 | Populating the fields after barcode scan
7 | Generating unique identifier for the image/text file with respect to individual user
8 | Saving the information into device storage if internet connection is not available
9 | Sending all the information to server through API/Webservice
10 | Syncing with server through API/Webservice if any information is saved in the temp storage of the device
11 | Displaying of feedogram after certain days of research starts through API/Webservice
12 | Prompting user for the baseline period ending
13 | Set my foodzone
14 | Generating build for review & bug fixes
15 | Android Build generation & Deployment of the app to the Google Play store by getting all the required information
16 | App crash testing
Web Development
Reports
1 | Reports generating Feedogram
2 | Daily report generation for the research co-ordinator showing all the feedogram
3 | Weekly report generation |  | Only intervention
4 | Feedogram report generation for the user in particular time baseline with weekend social jetlag
5 | Reports to study participant
6 | Meta reports
7 | Reports to study coordinator
8 | Dashboard for the system administrator
9 | Generating of baseline report
10 | Getting data from mTurk API
| Question entry with multiple types of option |  | Adv concept from phase2
| Data encryption and decryption functionality implementation |  | Adv concept from phase3
11 | Adding audit log capabilities
12 | Deployment to production server

## PHASE(4)
Salk Metabolic Phase#3 development
# | Item | Comments
iOS Development
Signup & Authentication
1
2
3
4
Study questionire & Reports
5
6
7
8
9
10
11
12
13
14
15
16
Android Development
Signup & Authentication
1
2
3
4
Study questionire & Reports
5
6
7
8
9
10
11
12
13
14
15
16
Web Development
1 | Participant can apply to multiple researches at once. After approved by any one, other will be canceled
2 | FNDDS database integration to display the calories count and other information
3 | Feedogram 4am to 4am display for each day
4 | Functionality to add/edit the Email content by the coordinator
5 | To build the JSON to send the all information for feedogram to the mobile app, to send the Image and other information |  | API
6 | Set the push notification content dynamically by the coordinator |  | CURD
7 | Eating duration or target set by participant. dispaly in the feedogram | API
8 | Report download of individual participant including images
9
10
11
12 | Deployment to production server

## Clinical flow
# | Item | Dev Hours | QA & Deployment | ETA | Comment | Questions
iOS Development
1 | Calendar - participant information after approved as per the date and time | 2 |  |  | Date signed up, date app activated, date of beginning of baseline, date of end of baseline etc
2 | Set reminder for medication and supplements | 16
3 | Respond push notification and send the answer
4 | Getting the date of intervetion start period from push notification and Saving the intervetion start date info in the calendar and showing the feedogram section | 4
5 | BMI calculator | 6
6 | Weight chart | 8
7 | Other tools | 24 |  |  | Blood Pressure measurement, Sleeping time measurement, Healthkit integration
Android Development
1 | Calendar - participant information after approved as per the date and time | 2 |  |  | Date signed up, date app activated, date of beginning of baseline, date of end of baseline etc
2 | Set reminder for medication and supplements | 16
3 | Respond push notification and send the answer
4 | Getting the date of intervetion start period from push notification and Saving the intervetion start date info in the calendar and showing the feedogram section | 4
5 | BMI calculator | 6
6 | Weight chart | 8
7 | Other tools | 24
API Development
1 | API- sent to all the information to the main server after sign up | 5 |  |  | ABRT stored data in the same server
2 | API to send the participant information after approved | 3 |  |  | Date signed up, date app activated, date of beginning of baseline, date of end of baseline etc
3 | API to send push notification for the date of intervetion start period | 4
4 | Analyze data and send them their comparatives in baseline and in the n week of intervention | 16 |  |  | Where n = 1,2 3... and Eating timing parameters and tag cloud, caloric content and other nutrition parameters.
API for view chart week wise
API for tag cloud week wise
API to send the all information for feedogram to the mobile app, to send the Image and other information
5 |  | 4
Web Development
Landing Page
1 | mock landing page which will list all studies that are currently recruiting | 6 |  |  | active ads will be dispalyed
2 | coordinator should be able to specify the content of the landing page | 3
3 | Questions about the smartphone | 4 |  |  | whether the participant knows the basic operations of a smartphone, three other apps they have downloaded | What will be the questions?
4 | Questionnaires for inclusion and exclusion criteria | 4 |  |  |  | Is it same for all the research studies?
5 | calculate the eligibility of the participant | 8
6 | Display the message as per the calculated output | 4
7 | Database design to store the information in this new server | 8
8 | Functionality after participant passes the preliminary screen | 6 |  |  |  | If participant select "May be", what will happen? whether the participant will follow the steps once again
9 | Functionality to save the personal information on choosing yes | 4
10 | This page will be more encryption as it will collect the personal information. [Q4] Name, Contact number, Email, Alternate phone number, Consent whether we can email/text or phone to set up appointment for an informed consent and introduction to the app., A Captcha and Submit | 6
11 | The sign up link from the app server will sent to his or her email id | 4
12 | Sign up funcationality
Appointment | [6 empty] | 34
13 | coordinator selects a few potential dates and times for appointments | 6 | 2 | 2015-02-02
14 | send the appointment dates over email and link will be active for 24 hours only | 3 | 1 | 2015-02-03 | link will not exipire
15 | confirm or decline the appointment date by the participant | 5 | 2 | 2015-02-03 | radio button with each date and time, participant will check one button and confirm | set reason
16 | New page to set the reason for decline and to request for new date |  |  |  | radio button for new time or not interested in study the submit
17 | Coordinator will review the answer and reset the time or reject the participant | 4 | 1 | 2015-02-04
18 | Final appointment confirmation email to the participant | 5 | 1 | 2015-02-04 | message will contain: with direction to the office, parking information and walking information to the lab. If lost, whom to text/call.
19 | Email notification for the appointment before one day | 3 | 1 | 2015-02-05 | a reminder is sent along with direction and link to decline
20 | Cancel appointment functionality |  |  |  | radio button for new time or not interested in study then submit | New time: coordinator will schedule again and same flow. if not interested then reject
21 | Rejection email if rejected
Clinical visit Report | [6 empty] | 49
22 | Save the consent date and status for each participant | 2 | 1 | 2015-02-05
23 | Generation of unique id for the participant | 8 | 3 | 2015-02-05 | First three alphaneumeric study code, followed by YYMM and a four digit number. New key if participant applied for new research
24 | App activation and baseline started | 2 | 1 | 2015-02-06 | Baseline end date will be set by coordinator
25 | Store anthropometric data | 4 | 1 | 2015-02-06 | Height, weight, body composition, blood pressure and heart rate
26 | Store actiwatch or any device serial number and date/time for each participant | 2 | 1 | 2015-02-09 | not mandetory, update while returns the same
27 | Added while creating Research | 5 | 2 | 2015-02-09 | Capture the total no. of time s/he eats or drinks, in the participant info for future use. It should be the default question | check box to be selected while creating Research
28 | Save the question and its answer to the database | 4 | 2 | 2015-02-10 | Modification as per the new changes
29 | record the medication or supplement information with the timing | 8 | 3 | 2015-02-12
30 | next visit appointment schedule
Baseline monitoring | [6 empty] | 40
31 | Baseline start functionality on specific day of the week | 1 |  | 2015-02-12 |  | Baseline will be start on approve
32 | Email notification before one day of baseline start |  |  |  | email will also have a link to a page that will have the instructions for using the app. The page will have a short video/animation/flowchart/power point of the app description.
33 | Creating the video/animation/flowchart/power point for the app | 16 | 2 | 2015-02-16
34 | On day 1 of the baseline, the system will send the first push notification | 4 | 1 | 2015-02-17 | Baseline message will be set by coordinator like encouraging note | base line start information? what will be the message
35 | On day 2 onwards, verify the eating count with the submitted eating count and send push notification to the participant as per the previous activity | 4 | 1 | 2015-02-17
36 | Email notification/Push notification before one day of baseline end with appointment confirm or change and direction | 5 | 2 | 2015-02-18 | Push notification is already done. It will work like appointment accept or decline functinality
37 | Daily report will be generate at 5 am | 4 | 1 | 2015-02-18
38 | Functionality to add other email ids to send the daily report
Second appointment | [6 empty] | 72
39 | Eating habit report generation functionality | 8 | 2 | 2015-02-20 | Add link on the today's appointment list. Report contain anthropometric data, feedogram | We are redirecting to the participant detail page where coordinator can find all the required information
40 | save the watch submit date | 2 | 1 | 2015-02-23
41 | Display and save the answers of Questionnarie for the second appointment
42 | Appointment schedule for blood collection | 3 | 1 | 2015-02-23 | Email with direction
43 | Email/push notification before one day of blood collection date | 3 | 1 | 2015-02-23 | Email with direction to the blood collection center
44 | Update the database after the blood work is done | 5 | 1 | 2015-02-24 | Store all the blood lab report data into the db
45 | Intervention period will start on update the database | 2 | 1 | 2015-02-24 |  | Automatic start or coordinator will set the date?
46 | Email/push notification before one day of intervention start with a link to withdraw | 3 | 1 | 2015-02-25 | reason ( delay or quit)
47 | Withdraw functionality | 6 | 2 | 2015-02-26 |  | How will it work? is it like dropout
48 | Push notification for encouraging note in the intervention period | 4 | 2 | 2015-02-26 | For intervention
49 | Questionnaire on the first three days of intervention | 6 | 2 | 2015-02-27 | did you feeling energetic like pushnotification will be send and ans will be recorded
50 | Monthly Report | 8 | 3 | 2015-03-02 | only for intervention | Chart in mobile
51 | notification for the appointment on the 7th week | 4 | 1 | 2015-03-03
Security | [6 empty] | 44
| Encryption and Decryption of API | 16 | 2 | 2015-03-05
| Activity management | 8 | 2 | 2015-03-06
| Load testing |  | 8 | 2015-03-09
| Penitration testing |  | 8 | 2015-03-10
3rd party integration | [6 empty] | 76
| Rnd FNDDS Database integration | 16 | 3
| Coordinator can search food and set caloreis | 16 | 4
| mTurk integration for annotation | 32 | 5
| Sidekiq for background execution | 16 | 2 |  | image store, email and other
Report | [6 empty] | 10
| Individual participant report in csv or excel | 4 | 1 |  | With the annotations and timing | need more information
| Download all the images in ziped format | 4 | 1
Sending of data without annotation | [6 empty] | 52
| Storing the images and other info from mobile app without annotation | 32 |  |  | DB arch. change
| Coordinator or different participant will annotate them (API for mobile) | 8 | 2
| Save the annotation wrt image after save | 8 | 2
New requirements(not in flow or documents) or modification of existing | [6 empty] | 70
| Set the push notification content dynamically by the coordinator | 6 | 2
| Eating duration or target set by participant. display in the feedogram API | 6 | 1 |  | Feedogram dispaly change with a border
| Functionality to add/edit the Email content by the coordinator | 8 | 2
| Feedogram 4am to 4am display for each day | 10 | 2
| Participant can apply to multiple researches at once. After approved by any one, other will be canceled | 16 | 3
| Set the weight measure - API | 4 | 1
| If participant sends only text annotation, then previous image should not be mapped to it | 8 | 1
| Question on the phone |  |  |  |  | Doubt: where to display
Deployment | [6 empty] | 6
| Deployment to production server | 4 | 2
BUG | [6 empty] | 6
| Validate the calculation for the eating duration |  |  |  |  | Need more information on that

## clinical_flow_raw
SL# | Module | Tasks | Hours | Status | Remark | Queires
| Landing Page | Landing page is connected to a specific coordinator and a study. [Can Andolasoft set up a mock landing page, so that we can test the sign up step] If a coordinator is running multiple studies ( say feeding pattern and sleep, feeding pattern and heart function, feeding pattern and diabetes etc.) the landing page will list all studies that are currently recruiting and the prospective participant can select only one study and go the next page.
The coordinator should be able to specify the content of the landing page.
Questions about the smartphone [Q1], if the participant knows the basic operations of a smartphone, three other apps they have downloaded etc. If they answer Yes they have a compatible smartphone and know the basic function of the phone, they go to next. Else …. [thank you note 1] “thanks for your interest..”
Next inclusion/exclusion criteria [Q2] will be study specific. No personal information is to be given in the inclusion/exclusion criteria (no name, or contact). But the participants will input anthropometric data [Q3] their gender, age, weight, height, race etc.
Message after inclusion and exclusion criteria are met.
If the person does not meet the eligibility criteria- then [thank you note 2] “Thank you for your interest… but …..”
If the participant passes the preliminary screen, there will be a message saying along the line [Message 1] “you meet the criteria for participating in the study. The study will involve visit to the lab, after 3 weeks another visit to the lab, etc. (Overview of the study without giving out the details but to say how long and what it involves.) Would you like to participate in the study?” If the person says NO – then … [thank you note 3] “ thank you for ….” If the person says, may be – I will think about it, but need to talk to someone? If the person says yes – then the next page appears which will have more strict encryption for personal information:
This page will be more encryption as it will collect the personal information. [Q4] Name, Contact number, Email, Alternate phone number, Consent whether we can email/text or phone to set up appointment for an informed consent and introduction to the app., A Captcha and Submit
All information from the sign up page will be sent to server (1.3. - phone information, answers to inclusion, exclusion criteria, anthropometric data, name, email etc.
The sign up information is shown in the system.
The study coordinator gets an alert in her/his email – [message 2] “someone signed up”.
The person gets an email [message 3] that someone will contact him/her shortly.
| Setting up first appointment and app activation. | Appointment for informed consent and baseline measurements. The coordinator selects a few potential dates and times for informed consent and the system generates an automatic message [message 4] asking the participant to select a data/time within 24 h.
[message 4] There is a link embedded in the email to confirm or decline. If the person declines, there is a link to [a page] where the person says why s/he declines. Whether s/he needs another time for appointment or not interested in the study.
Final confirmation is sent [message 5] with direction to the office, parking information and walking information to the lab. If lost, whom to text/call.
One day before the appointment, a reminder [message 6] is sent along with direction. If the person wants to cancel there is a link to cancel – same as above.
| During the appointment | The coordinator or a designate will administer Informed consent. Consent date and the person consented will be recorded in the database. If the person does not consent, that is also recorded in the database.
Unique ID generation – coding the participant. The system generates a unique participant ID. [First three alphaneumeric study code, followed by YYMM and a four digit number]. Although we had initially thought of a more complex alphaneumeric code, the clinical coordinators don’t like such codes.] The system also generates an activation code. All past and future information is now linked to this unique participant ID.
App activation: App download, App activation
All key events specific to the participant is also populated in the calendar. Date signed up, date app activated, date of beginning of baseline, date of end of baseline etc.
Anthropometric data is recorded. Height, weight, body composition (lean%, fat%, water%, and rest%), blood pressure (Systolic, diastolic), heart rate. Entered to database.
If an actiwatch or any other device is given to the person, that device serial number is also included in the database and the device is activated. Date of data collection (starting date and end date) are also entered. Sampling frequency (30sec, or 1min) is also entered.
Questionnaires: At least one Nutrition and wellness questionnaire is administered [Q5]. (is it done from the app or from a website? How to connect the answers to the unique ID?). How are answers to the questionnaires entered to the database. (If the person says s/he eats or drinks total X times or more, that information is entered in the field used for everyday validation. See sections on what happens after the beginning of the baseline)
For current medications and supplements - If the person is taking any medication or supplement, it is also recorded in the database.
The coordinator explains the app, the actiwatch (or any other device if given to the participant), demonstrates some features of the app. If there are current medications or supplements, the coordinator can show how to set reminder for medications/supplements.
Next appointment is set for the end of the baseline period. The coordinator shows the participant the calendar function in the app.
| Baseline monitoring | If there is a specific day of the week when the baseline starts, the day before, the system will send an automatic email prompting to start. The email will also have a link to a page that will have the instructions for using the app. The page will have a short video/animation/flowchart/power point of the app description.
On day 1 of the baseline, the system will send the first push notification.
On day 2 of the baseline the following notifications will be sent – based on day 1 progress
If the person logged at least the number of events that the person said s/he eats in a day (X), an encouraging note prompting the use to continue recording eating events.
If the number of events recorded in the day 1 was less than X (or 0) . The note will gently prompt the user to log every event and a link to the app demo or (ANY SUGGESTION HERE? [ this text needs to be crafted well]
On day 3- end of baseline period:
On day 3 if the person continues to record events, there will be an encouraging note.
Every day there will be a push notification and the response to push notification will be logged.
If there number of events logged is more than X for 3 consecutive days, the person will not receive any more push notification unless the number of events/day drops to less than X. [PLEASE COMMENT]
If there is no event AND no response to push notification for one complete day, there will be a different message. [PLEASE COMMENT].
If there is no event AND no response to push notification for 2 complete day, there will be a different message. [PLEASE COMMENT]
One day before the baseline ends, the system will send an automatic reminder for the upcoming appointment and the person has to confirm or request a change (same as before). Detail direction etc. will also be given.
Every day, the system will send a summary at 5am local time to the coordinator (and any other person about the study). In the back-end there should be a mechanism to add these emails. What will be the content of this email?
Second appointment
On the morning of the appointment the system will generate a report for the person’s eating habit. Which parameters will be included? And the Coordinator will decide if the person is eligible for participation in the study.
Criteria to progress to intervention: Typically sends at least 5 events per day for at least 2/3rd of the days, did not have significant drop in the number of events/day between the first week and the last week, Eating interval more than 14 h, Eats more into late night (end of the eating interval after 10pm).
During the appointment, the participant will return the actiwatch (if given to the person). Data will be downloaded and visualized for sleeping duration. If the person turns out to be a shift worker, s/he may not qualify for the intervention.
Anthropometric data (weight, waist circumference, hip circumference, blood pressure, body composition (if possible) will be recorded and entered into the system. If there is more than 1% change in body weight in the baseline period, the person will not qualify for the intervention.
Payment for the first part of the study will be made in cash if it was mandated by IRB.
If the person qualifies for the intervention
S/he will be asked if s/he is interested in the intervention – s/he will be informed of the intervention and the risk/benefit etc. before the informed consent.
Informed consent for the intervention.
Information on the intervention – powerpoint slides and additional information on the app.
Additional questionnaires (to be decided)
Appointment for blood work and direction to the center will be given. If the person has to schedule his/her appointment with the blood collection center, it will be noted in the database. The official intervention will not begin until after the blood collection.
Intervention app activation. This will be delayed until after the blood collection date.
If the person is to be given a watch- watch activation and entry in the database.
On the day before the blood sample appointment, there will be an automatic email and direction to the blood collection center.
On the day after the scheduled blood collection day, the coordinator will confirm with the participant that the blood work was done. This will clear all requirements for start of the intervention.

## by_7_Jan
SL# | Web
1 | Question entry with multiple types of option
2 | Landing Page Changes as per the clinical flow mock landing page which will list all studies that are currently recruiting coordinator should be able to specify the content of the landing page Questions about the smartphone Questionnaires for inclusion and exclusion criteria calculate the eligibility of the participant Display the message as per the calculated output Database design to store the information in this new server Functionality after participant passes the preliminary screen Functionality to save the personal information on choosing yes "This page will be more encryption as it will collect the personal information. [Q4] Name, Contact number, Email, Alternate phone number, Consent whether we can email/text or phone to set up appointment for an informed consent and introduction to the app., A Captcha and Submit" The sign up link from the app server will sent to his or her email id
API
1 | API- sent to all the information to the main server after sign up
2 | API to send the participant information after approved
3 | API to send push notification for the date of intervetion start period
4 | Set the weight measure
5 | API to display the feedogram on the mobile device
Mobile
1 | Set my foodzone
2 | Displaying of feedogram after certain days of research starts through API/Webservice
3 | Show intervention and tag cloud
4 | Calendar - participant information after approved as per the date and time
5 | Getting the date of intervetion start period from push notification and Saving the intervetion start date info in the calendar and validation to show the feedogram
6 | BMI calculator
7 | Prompting user for the baseline period ending

## Credentials
iPhone App (Staging Server)
http://54.164.78.180/
Coordinator Credential
-----------------------------
sudhansu.test4@gmail.com / test1234
Research Study - Vision
App Credential
--------------------
72C9Aa / su.dhansu.test.5@gmail.com
Android App (QA Server)
http://192.168.2.170:3003/
Coordinator Login
----------------------
sudhansu.patro@andolasoft.com / test1234
Research Study - Medical genetics
App Credential
-------------------
VkspCc / niloferjohn12.3@gmail.com
For iOS8 iPAD
SCwueM
sudhansuandola@gmail.com

## iOS_by_jan7
SL# | Task to be done by JAN 5 | HOURS | Developer | Status
Set my foodzone
| To split the marker annnotation view | 2014-12-24 | SHL | CMPL
| To change the color of the rows according to day and night | 2014-12-29 | SHL | CMPL
| Adding the food name from coomon food section | 2014-12-25 | SHL | CMPL
| UI layout changes in enlarge view. | 2014-12-29 | SHL | WIP
| Add limit to 10 rows. | 2014-12-27 | SHL | CMPL
| To enlarge the image and show in sliding view | 2014-12-24 | SHL | CMPL
| Fixing the data shrinc with server food section | 2014-12-26 | SHL | CMPL
Calendar
| Calendar - participant information after approved as per the date and time | 2014-12-26 | SHL | CMPL
Feedogram
| Displaying of feedogram after certain days of research starts through API/Webservice | 2015-01-07 | MRM | CMPL
| Add start and end target. | 2015-02-02 | SHL | TBD
| Add aggregate in feedogram | 2015-02-02 | SHL | TBD
Intervention and tag cloud
| Show baseline and intervention results in chart view | 2014-12-24 | MRM | CMPL
| Showing tag cloud by clicking the bars | 2014-12-31 | MRM | CMPL
BMI calculator
| Adding BMI calculation | 2015-01-02 | SHL | CMPL
| Showing BMI chart | 2015-01-05 | MRM | CMPL
| Call BMI api | 2015-02-02 | SHL | TBD
Pushnotification
| Prompting user for the baseline period ending | 2015-01-05 | SHL | CMPL
| Getting the date of intervetion start period from push notification and Saving the intervetion start date info in the calendar and validation to show the feedogram | 2015-01-05 | SHL | CMPL
Minor issues to be fixed
| If food item is exist in db, then that item add in text box in common food sectin and camera section. | 2014-12-24 | SHL | CMPL
Arrenge the food buttons.
| Change the uilayout of common food section.(6 static buttons and time picker display in uiaction sheet). | 2014-12-26 | MRM | CMPL
| Showing actionsheet with time picker | 2014-12-29 | SHL | CMPL
| Fix icarousel layout issue. | 2015-01-13 | SHL | WIP
| Changed the layout and functionality of bmi calculator view. | 2015-01-13 | SHL | CMPL
| After selecting a time button in this text tab, the time button should change color or brightness to show what is selected. | 2015-01-14 | SHL | CMPL
| DEVICE TOKEN NULL | 2015-01-16 | SHL | CMPL
| IOS 7 AND 8 CONDITION CHECK | 2015-01-16 | SHL | WIP
| ADDRESS ERROR CHECK | 2015-01-16 | SHL | CMPL
| ALERT VIEW Cancel | 2015-01-16 | SHL | CMPL
| ADDING LOADER | 2015-01-16 | SHL | WIP
iOS 8 fixes
| Getting lat and long using Location manger | 2014-12-24 | MRM | CMPL
| FILE MANAHEMENT: date format issue | 2014-12-26 | MRM | CMPL

## Android_by_jan7
SL# | Task to be done by JAN 5 | HOURS | Developer | Status
| Login |  |  | CMPL
| Removing the location service off msg from login page | 2014-12-24 |  | CMPL
| Set my foodzone |  |  | CMPL
| To split the marker annnotation view | 2014-12-24 | SRS | CMPL
| To change the color of the rows according to day and night |  |  | CMPL
| Adding the food name from coomon food section |  |  | CMPL
| UI layout changes in enlarge view. |  |  | CMPL
| Add limit to 10 rows. | 2014-12-24 | SRS | CMPL
| To enlarge the image and show in sliding view | 2014-12-24 | SRS | CMPL
Calendar
| Calendar - participant information after approved as per the date and time |  | SRS | CMPL
Feedogram
| Displaying of feedogram after certain days of research starts through API/Webservice |  | SRS
Intervention and tag cloud
| Show baseline and intervention results in chart view |  | SRS
| Showing tag cloud by clicking the bars |  | SRS
BMI calculator
| Adding BMI calculation |  | SRS | CMPL
| Showing BMI chart |  | SRS
Pushnotification
| Prompting user for the baseline period ending |  | SRS
| Getting the date of intervetion start period from push notification and Saving the intervetion start date info in the calendar and validation to show the feedogram |  | SRS