## 05_14_2015
SL# | Task | Dev hr | QA hr | Resource | Status | Comment | API | Dev hr | Status
Menu medley
1 | Change all the Tag cloud text with Menu Medley | 0.5 |  | SLN | DONE
2 | In New tag cloud all over the screen looks messy and so far apart difficult to say if items are larger than others | 1.5 |  | SLN | ABRT | Assumed: weekly food count = 35 & max food frequency = 20 So, we think no need to change the current display style. If required then will change | Send the weekly count of foods | 1 | DONE
Sleep analysis chart
3 | Add time axis on Sleep chart | 0.5 |  | SUM/SLN | DONE | API changes
4 | Display 2 weeks data and layout adjustment | 1.5 |  | SUM/SLN |  |  | Changes to send 2 weeks data | 1 | WIP
5 | Set target in sleep analysis | 1 |  | SUM/SLN | DONE
6 | Weekday aggregate and weekend aggregate | 1 |  | SUM/SLN |  |  | Logic to calculate aggregate and to send in API | 4
7 | Weekend jetlag | 1 |  | SUM/SLN |  |  | Logic to calculate jetlag | 2
Health tools section
8 | Display the tool information on every pages | 0.5 |  | SBS | DONE
9 | And inside the tool information display the range information | 2 |  | SBS | DONE | Need RND for blood sugar range
10 | Add wheel for data input where feasible |  |  | SBS | DONE
11 | Add color scale to display the range for BMI, BP, and BS | 6 | 2 | SBS | DONE | Except Blood sugar
Calendar
12 | Change the date color as per the round circle and use bold | 2 |  | SBS | DONE | Need to go through the Calendar library
| To save and retrieve data from the Calender info in the database | 1 |  | SBS | DONE
13 | Filter the calendar info list as per the month selected | 4 | 0.5 | SBS | DONE
14 | display the upcoming events as per the current date | 1 |  | SBS | DONE
Feedogram
15 | Remove the vertical lines at 6am and 6pm | 0.5 |  | SUM/SLN | DONE
16 | Increase the thickness of target lines to make it more prominent | 0.5 |  | SUM/SLN | DONE
17 | Display 2 weeks of data with layout changes | 2 |  | SUM/SLN | DONE |  | Changes to send 2 weeks data | 1 | DONE
18 | Display start and end times for Weekday and weekend aggregate line | 1 |  | SUM/SLN | DONE
Feedogram History
19 | Show the weekday range 08/02 - 08/07 XY hr instead of I#1 XYhr | 0.5 |  | SUM/SLN | DONE |  | API changes to send date ranges | 1 | DONE
20 | Display the target hours and start & end time | 0.5 |  | SUM/SLN | DONE |  | To send required information | 0.5 | DONE
21 | Remove Set target button and make the "Feedogram" button larger | 0.5 |  | SLN | DONE
22 | Display information message "Tap on the bar to view Menu Medley" | 0.5 |  | SLN | DONE
Research Info
23 | Rename to "Research Contact Info" | 0.5 |  | SLN | ABRT
24 | Display only coordinator contact info and remove all the tabs | 0.5 |  | SLN | ABRT
25 | Add PI names and Email | 0.5 |  | SLN | DONE
Splash screen
26 | Display a cool pic with the clock ticking around if waiting for download | 1 |  | SLN | DONE
27 | Remove "study 2015" |  |  | SLN | DONE
28 | Change the address below App name "Satchin Panda Lab, Salk Institute, La Jolla, California, USA" | 0.5 |  | SLN | DONE
Login Screen
29 | Remove "study 2015" |  |  | SLN | DONE
30 | Change the address below App name "Satchin Panda Lab, Salk Institute, La Jolla, California, USA" | 0.5 |  | SLN | DONE
31 | Remove the shaded square | 0.5 |  | SLN | DONE
32 | Display the message "Synchronizing data with server. It may take several minutes" while sync data | 0.5 |  | SLN | DONE
33 | Rename the text "LOGIN TO YOUR ACCOUNT" with "Begin Participation" | 0.5 |  | SLN | DONE
34 | information for access code "Access code: sent to you after signing the consent document." | 0.5 |  | SLN | DONE
35 | Reverse the email and access code position | 0.5 |  | SLN | DONE
36 | Mockup with different color for login page | 0.5 |  | SUM | DONE
Take picture section
37 | Add Feedback, Feedogram, menu medley, Health tool page icons at the header bar | 0.5 |  | SLN | DONE
38 | In middle section display all the today's data in scroll view | 2 |  | SLN | DONE | Displayed the current date's Feedogram
39 | Display food count and water count instead of "Recently captured" text | 1 |  | SLN | DONE
40 | Add Sleep and Exercise icons on the bottom left corner | 0.5 |  | SLN | DONE
Feedback Feature
41 | Page to give feedback | 2 |  | SLN | DONE | To design and send email | API to save feedback in the database and send email to coordinator | 3 | DONE
Miscellaneous
| in Research contact page, Rename the research tab to research support and dsplay the research support page | 1 |  | SLN | TBD
| Total | 42 | 2.5 |  |  |  | API | 13.5

## 06_09_2015
SL# | Task | Dev hr | QA hr | Resource | Status(iOS) | Status(Android) | Comment | API | Dev hr | Status
Login Page
1 | Access Code: This app is for research use. You will receive the access code after consenting for the research study. |  |  |  |  | Android DONE
2 | It may take several minutes --> This may take several minutes
Theme
3 | Remove background image and use only plain background |  |  |  |  | Android DONE
4 | Changed the menu page background color to light blue color |  |  |  |  | Android DONE
5 | Change the menu icon to white |  |  |  |  | Android DONE
Research Contact
6 | Remove all the tab |  |  |  |  | Android DONE
7 | Add Research feedback form here |  |  |  |  | Android DONE
8 | Change the background color and add bulb for idea or letter image |  |  |  |  | Android DONE
9 | Remove the email id content and display only "Contact researcher" |  |  |  |  | Android DONE
10 | Success message should be "Feedback sent!" |  |  |  |  | Android DONE
Take Picture
8 | if no one day feedogram data available, display "Start taking pictures to see today’s progress" |  |  |  |  | Android DONE
9 | Food & bev --> Food & Bev. (capitalize b, add full stop after abbreviation) |  |  |  |  | Android DONE
10 | The numbers and text appear misaligned vertically. (e.g. Medicine and 0) |  |  |  |  | Android DONE
Common Food
11 | Display the annotation with initial capital letter |  |  |  |  | Android DONE
BMI
12 | Number could start out at 2ft and 50lbs |  |  |  |  | Android DONE
13 | Add "BMI" label to the colorbar, it's not obvious what it is otherwise. |  |  |  |  | Android DONE
14 | Make the lines further apart so green zone doesn’t look so small. Underweight side should be just as red as overwt. Scale from 15 to 45. |  |  |  |  | Android DONE
15 | In Weight chart, remove the chart title "weight" |  |  |  |  | Android DONE
16 | Weight --> My Weight (lbs.) |  |  |  |  | Android DONE
17 | Space needed between date and month name, (13May --> 13 May). Align them, so that they, don’t overlap the axis – same in slide 16. |  |  |  |  | Android DONE
Blood Pressure
18 | Too much green, spread out lines.Scale from 50 to 200 on systolic and Scale 40 to 150,Also if 90/60 should be red on left side, just like BMI |  |  |  |  | Android DONE
19 | In Blood Pressure chart, remove the chart title "Blood Pressure" |  |  |  |  | Android DONE
20 | Delete “Blood pressure result”, Put (mm Hg) after “level” on side |  |  |  |  | Android DONE
21 | Blood pressure level --> Blood Pressure (mmHg) |  |  |  |  | Android DONE
22 | There's no need to change the marker type (square vs diamond) when the colors are different for SBP and DBP.
23 | Change the reference from Wikipedia to NIH http://www.nhlbi.nih.gov/health/health-topics/topics/hbp |  |  |  |  | Android DONE
24 | Needs a comma after Diastolic
25 | Decrease font size of prehypertension so on one line |  |  |  |  | Android DONE
Blood Sugar
26 | Blood Sugar Chart ----> Blood Sugar |  |  |  |  | Android DONE
27 | Delete “Blood sugar result” |  |  |  |  | Android DONE
28 | There are two overlapping labels around 150.Not clear why.
29 | Insert mg/dL after level |  |  |  |  | Android DONE
30 | Delete the irrelevant sentence "Normal value ranges ..." |  |  |  |  | Android DONE
31 | no units are mentioned. So add a sentence Units are mg/dL. |  |  |  |  | Android DONE
32 | Time of Check --> Time Checked |  |  |  |  | Android DONE
Exercise
33 | Might be interesting to see aerobic vs strength to compare AHA guidelines.
34 | Exercise is misspelled everywhere on this |  |  |  |  | Android DONE
35 | Change background to plain white – same for other screens with similar layout. |  |  |  |  | Android DONE
36 | Your exercise details has been --> Your exercise details have been |  |  |  |  | Android DONE
37 | Difficulty level --> Activity level. Also change in previous screen. |  |  |  |  | Android DONE
38 | See comments from slide 21. #1 exercise is walking. I can't find it on the list. Should be first
39 | Change to Physical Activity history |  |  |  |  | Android DONE
40 | Add color legend – light, medium, intense physical activity. |  |  |  |  | Android DONE
Slide Bar
41 | Get rid of research contact Rid of blue background on icons, make icons white and dropback page a lighter shade of the power |  |  |  |  | Android DONE
Feedogram
42 | Still like “Actual” over weekday Trophies at end of day for making Target hours??
43 | Change title to “Feedogram History” |  |  |  |  | Android DONE
44 | Why there are two weekdays averages (green)
45 | this section of Feedogram -> this section.
Menu Medley
46 | Medly --> Medley |  |  |  |  | Android DONE
47 | This font should be much funner and
48 | bigger. Make sure the smallest font is at bigger. Make sure the smallest font is at least 18 size. The tiny fonts cannot be read.
49 | Instead of cancel button, can we have “Back”, “Previous week”, “next week”?
50 | At the end of the list show water, medications. |  |  |  |  | Android DONE
Food Collage
51 | Put a sync button for past weeks.
52 | Sync past version pics
53 | Can this be shown on a transparent background over the map.
54 | In food collage date range, the dates are wrongly shown. Instead of 2015, it shown 2014 for Jan-June.
55 | change date format to 01-Jan-2015 etc
Calendar
56 | Trophy can be added to calendar day for making target
57 | Intervention end date --> Intervention Ends On 2015-08-02 --> 2nd Aug 2015 Or 2 Aug 2015 |  |  |  |  | Android DONE
58 | Change date format from 2015-08-02 etc --> 2 Aug 2015 etc |  |  |  |  | Android DONE
Wieght Chart
59 | Put lbs after weight on side |  |  |  |  | Android DONE
Track Your Health
60 | Different font for these tabs
Sleep History
61 | Set your .. to bed --> Enter Bedtime |  |  |  |  | Android DONE
62 | Set when you woke up --> Wake Up Time |  |  |  |  | Android DONE
63 | Awake at: --> I Woke Up At |  |  |  |  | Android DONE
64 | Should auto set to PM for first question.
65 | Sleep Analysis : Same as last page?
66 | If “was this enough sleep?” is NO – Then turn bar to orange. Add this to FAQs
67 | Get a star for meeting sleeping goal
Pushnotifications
68 | Make note of being on or off
69 | Push-notification --> Push Notifications
FAQ
70 | Medly --> Medley |  |  |  |  | Android DONE
71 | How can I view --> How can I view the |  |  |  |  | Android DONE
72 | Can I use the app in offline? --> Can I use the app offline? |  |  |  |  | Android DONE
73 | Why feedogram menu is not coming? --> Why does my feedogram fail to display? |  |  |  |  | Android DONE
74 | Can I record medicine... --> How do I record my medicine intake? |  |  |  |  | Android DONE
75 | How to send food image? --> How do I send my food photo? |  |  |  |  | Android DONE
76 | Can I send multiple Food.. --> F of food should be lowercase/few time ago --> a little while ago |  |  |  |  | Android DONE
77 | is there any way to ... -> When's my next appointment? |  |  |  |  | Android DONE
78 | You can also refer the ...--> You can also refer to the events in the calendar section. |  |  |  |  | Android DONE
Medicine Reminder
79 | Are you sure to ... --> Please confirm that you want to edit this reminder. |  |  |  |  | Android DONE
80 | Enter your medicine name --> Enter medicine name. |  |  |  |  | Android DONE