## SalkMetabolic_New
SalkMetabolic Task list
Sl# | Type | Task | Dev in hr | QA in hr | Comments
iOS Development
1 | New | Push notification On/Off | 1 | 1
2 | New | Other tools | 35 | 5 | Health Kit Integration
3 | New | Food Collage | 3 | 2
4 | New | Feedogram display changes | 24 | 2 | As per the provided document"Feedback_20150228"
5 | New | Feedogram Filter for All, water and medicine | 8 | 2 | As per the provided document"Feedback_20150228"
| New | Weekday and Weekend aggregate display changes | 8 | 2 | As per the provided document"Feedback_20150228"
| New | Active timer for last calorie intake | 4 | 2 | As per the provided document"Feedback_20150228"
6 | New | In Feedogram page, display images or food collage as per the selected area for the particular time range | 4 | 2
7 | New | Set reminder for medication and supplements | 4 | 2 | As per the understanding, we have completed this functionality on the Web and push notification is going as per the scheduled time. But, now this functionality need to add in the Mobile app and local reminder like alarm
7 | Pending | New layout integration | 24 | 6 | After the final layout provided
8 | Pending | Other tools (If Health kit will be implemented then it will be skipped) | 16 | 4 | Blood Pressure measurement, Sleeping time measurement. It was not specified and assigned on 26th Feb 2015
9 | Pending | Auto layout | 40 | 6 | After the final layout provided
10 | Pending | API call Encryption | 16 | 2
11 | Pending | Help | 8 | 1 | After the final layout provided
|  | Total | 91 | 20
Android Development
1 | New | Push notification On/Off | 1 | 1
2 | New | Other tools | 35 | 5 | Health Kit Integration
3 | New | Food Collage | 3 | 2
4 | New | Feedogram display changes | 24 | 2 | As per the provided document
5 | New | In Feedogram page, display images or food collage as per the selected area for the particular time range | 4 | 2
6 | New | Set reminder for medication and supplements | 4 | 2 | As per the understanding, we have completed this functionality on the Web and push notification is going as per the scheduled time. But, now this functionality need to add in the Mobile app and local reminder like alarm
7 | Pending | New layout integration | 24 | 6 | After the final layout provided
8 | Pending | Other tools(If Google fit will be implemented then it will be skipped) | 16 | 4 | Blood Pressure measurement, Sleeping time measurement. It was not specified and assigned on 26th Feb 2015
9 | Pending | Layout adjustment | 40 | 6 | After the final layout provided
10 | Pending | API call Encryption | 16 | 2
11 | Pending | Help | 8 | 1 | After the final layout provided
|  | Total | 71 | 14
API Development
1 | New | Push notification On/Off | 4 |  | To update database
2 | New | Food Collage | 8 |  | API to send required images
3 | New | Feedogram display changes | 16 |  | As per the provided document
4 | New | In Feedogram page, display images or food collage as per the selected area for the particular time range | 16
5 | New | Set reminder for medication and supplements | 4 |  | API for synch, add/update
6 | Pending | API call Encryption | 16
7 | Pending | Other tools | 16 |  | To save data related to Blood Pressure and Sleeping time
|  | Total | 48
Web Development
1 | New | FNDDS Database integration | 24 | 6 | Need to do RnD
2 | New | Coordinator can search food and set caloreis using FNDDS | 24 | 4 | Need to do RnD
3 | New | mTurk integration for annotation | 24 | 6 | Need to do RnD
4 | New | Functionality to add/edit the Email content by the coordinator | 10 | 2
5 | New | Visit question in a new page without login and functionality to save | 6 | 2
6 | Pending | Blood report functionality | 6 | 2
7 | Pending | Other Fixes | 24 | 4
|  | Total | 88 | 20

## SalkMetabolic_Pending
SalkMetabolic Task list
Sl# | Type | Task | Dev in hr | QA in hr | Comments
iOS Development
7 | Pending | New layout integration | 24 | 6 | After the final layout provided
8 | Pending | Other tools (If Health kit will be implemented then it will be skipped) | 16 | 4 | Blood Pressure measurement, Sleeping time measurement. It was not specified and assigned on 26th Feb 2015
9 | Pending | Auto layout | 40 | 6 | After the final layout provided
10 | Pending | API call Encryption | 16 | 2
11 | Pending | Help | 8 | 1 | After the final layout provided
|  | Total | 104 | 19
Android Development
7 | Pending | New layout integration | 24 | 6 | After the final layout provided
8 | Pending | Other tools(If Google fit will be implemented then it will be skipped) | 16 | 4 | Blood Pressure measurement, Sleeping time measurement. It was not specified and assigned on 26th Feb 2015
9 | Pending | Layout adjustment | 24 | 6 | After the final layout provided
10 | Pending | API call Encryption | 16 | 2
11 | Pending | Help | 8 | 1 | After the final layout provided
|  | Total | 88 | 19
API Development
6 | Pending | API call Encryption | 16
7 | Pending | Other tools | 16 |  | To save data related to Blood Pressure and Sleeping time
|  | Total | 32
Web Development
1 | Pending | Blood report functionality | 6 | 2
2 | Pending | Other Fixes | 24 | 4
|  | Total | 30 | 6