## SalkMetabolic_New
SalkMetabolic New Task List
Sl# | Type | Task | Dev in hr | QA in hr | Comments
iOS Development
1 | New | Push notification On/Off for different feature | 8 | 1 | Note, Eating time, Medication and suppliment, All
2 | New | Other tools (Health Kit Integration) | 35 | 5 | iOS rules and app compatibility And API call to send the data to server
3 | New | Feedogram page display changes | 8 | 2 | As per the provided document"Feedback_20150228"
4 | New | Feedogram layout implementation | 36 | 4
5 | New | Feedogram display on filter for All, water and medicine | 8 | 2 | As per the provided document"Feedback_20150228"
6 | New | Weekday and Weekend aggregate display changes | 8 | 2 | As per the provided document"Feedback_20150228"
7 | New | Active timer for last calorie intake | 4 | 2 | As per the provided document"Feedback_20150228"
8 | New | view chart changes by clicking the history in Feedogram page | 36 | 4 | As per the provided document"Feedback_20150228"
9 | New | small thumbnail image of the food will pop-up randomly from the feedogram hash marks | 16 | 4
10 | New | In Feedogram page, display images or food collage as per the selected area for the particular time range | 16 | 4 | To make the paricular area as per the time range per week clickable and Call the API to send image
11 | New | Food Collage | 8 | 2
12 | New | Set reminder for medication and supplements | 16 | 2 | As per the understanding, we have completed this functionality on the Web and push notification is going as per the scheduled time. But, now this functionality need to add in the Mobile app and local reminder like alarm
7 | Pending | New layout integration | 24 | 6 | After the final layout provided
8 | Pending | Other tools (If Health kit will be implemented then it will be skipped) | 16 | 4 | Blood Pressure measurement, Sleeping time measurement. It was not specified and assigned on 26th Feb 2015
9 | Pending | Auto layout | 40 | 6 | After the final layout provided
10 | Pending | API call Encryption | 16 | 2
11 | Pending | Help | 8 | 1 | After the final layout provided
|  | Total | 199 | 34
|  | Project Management and Scrum | 35
|  | Total Hour | 268
Android Development
1 | New | Push notification On/Off for different feature | 8 | 1 | Note, Eating time, Medication and suppliment, All
2 | New | Other tools (Google Fit Integration) | 35 | 5 | guideline to use and app compatibility And API call to send the data to server
3 | New | Feedogram page display changes | 8 | 2 | As per the provided document"Feedback_20150228"
4 | New | Feedogram layout implementation | 36 | 4
5 | New | Feedogram display on filter for All, water and medicine | 8 | 2 | As per the provided document"Feedback_20150228"
6 | New | Weekday and Weekend aggregate display changes | 8 | 2 | As per the provided document"Feedback_20150228"
7 | New | Active timer for last calorie intake | 4 | 2 | As per the provided document"Feedback_20150228"
8 | New | view chart changes by clicking the history in Feedogram page | 36 | 4 | As per the provided document"Feedback_20150228"
9 | New | small thumbnail image of the food will pop-up randomly from the feedogram hash marks | 16 | 4
10 | New | In Feedogram page, display images or food collage as per the selected area for the particular time range | 16 | 4 | To make the paricular area as per the time range per week clickable and Call the API to send image
11 | New | Food Collage | 8 | 2
12 | New | Set reminder for medication and supplements | 16 | 2 | As per the understanding, we have completed this functionality on the Web and push notification is going as per the scheduled time. But, now this functionality need to add in the Mobile app and local reminder like alarm
7 | Pending | New layout integration | 24 | 6 | After the final layout provided
8 | Pending | Other tools(If Google fit will be implemented then it will be skipped) | 16 | 4 | Blood Pressure measurement, Sleeping time measurement. It was not specified and assigned on 26th Feb 2015
9 | Pending | Layout adjustment | 40 | 6 | After the final layout provided
10 | Pending | API call Encryption | 16 | 2
11 | Pending | Help | 8 | 1 | After the final layout provided
|  | Total | 199 | 34
|  | Project Management and Scrum | 35
|  | Total Hour | 268
API Development
1 | New | Push notification On/Off for different feature | 8 |  | To update database for Note, Eating time, Medication and suppliment, All
2 | New | Food Collage | 12 |  | API to send required images
3 | New | Feedogram API modification to send the data as per the changed layout | 16 |  | Feedogram will be displayed in a weekly aggregate manner for each week. On clicking a weekly data, the feedogram will appear for that week
4 | New | Feedogram data on filter for All, water and medicine | 12
5 | New | Aggregate API changes | 6
6 | New | API for last food intake time | 6
7 | New | view chart API changes to send the other required information | 12
8 | New | In Feedogram page, display images or food collage as per the selected area for the particular time range | 16 |  | To send the images to form food Collage for the given time range for that week
9 | New | Set reminder for medication and supplements | 8 |  | API for synch, add/update
6 | Pending | API call Encryption | 16
7 | Pending | Other tools | 16 |  | To save data related to Blood Pressure and Sleeping time
|  | Total | 96
|  | Project Management and Scrum | 12
|  | Total Hour | 108
Web Development
1 | New | FNDDS Database integration | 24 | 6
2 | New | Coordinator can search food and set caloreis using FNDDS | 32 | 4
3 | New | mTurk integration for annotation | 32 | 6
4 | New | Functionality to add/edit the Email content by the coordinator | 12 | 4
| New | Feedogram layout changes to add box view per day | 12 | 4
5 | New | Visit question in a new page without login and functionality to save the data | 8 | 2
6 | Pending | Blood report functionality | 6 | 2
7 | Pending | Other Fixes | 24 | 4
Participant can
|  | Display participant's previous research dropout reason if he applied to new research after dropout | 8 | 4
|  | Total | 120 | 26
|  | Project Management and Scrum | 21
|  | Total Hour | 167

## SalkMetabolic_Pending
SalkMetabolic Pending Task List
Sl# | Type | Task | Dev in hr | QA in hr | Comments
iOS Development
7 | Pending | New layout integration | 40 | 6 | After the final layout provided and depends upon the layout
8 | Pending | Other tools (If Health kit will be implemented then it will be skipped) |  |  | Blood Pressure measurement, Sleeping time measurement. It was not specified and assigned on 26th Feb 2015. Changed as per new requirement
9 | Pending | Auto layout | 80 | 20 | After the final layout provided and depends upon the layout
10 | Pending | API call Encryption | 8 | 4
11 | Pending | Help | 16 | 2 | After the final layout provided and depends upon the layout
|  | Total | 144 | 32
|  | Total hour | 176
Android Development
7 | Pending | New layout integration | 40 | 6 | After the final layout provided and depends upon the layout
8 | Pending | Other tools(If Google fit will be implemented then it will be skipped) |  |  | Blood Pressure measurement, Sleeping time measurement. It was not specified and assigned on 26th Feb 2015. Changed as per new requirement
9 | Pending | Layout adjustment | 80 | 16 | After the final layout provided and depends upon the layout
10 | Pending | API call Encryption | 8 | 4
11 | Pending | Help | 16 | 2 | After the final layout provided and depends upon the layout
|  | Total | 144 | 28
|  | Total hour | 172
API Development
6 | Pending | API call Encryption | 16
7 | Pending | Other tools |  |  | To save data related to Blood Pressure and Sleeping time
|  | Total | 16
Web Development
1 | Pending | Blood report functionality | 6 | 2
2 | Pending | Eating Frequency logic change | 5 | 4 | waiting to get it from client
3 | Pending | Other Fixes | 40 | 16
4 | Pending | Individual participant report and all the images download for that participant | 12 | 4
|  | Total | 63 | 26
|  | Total hour | 89