## New_TBD_tasks
SalkMetabolic New Task List
Sl# | Task | Dev in hrs | QA in hrs | Comments
iOS Development
1 | Push notification On/Off for different feature | 12 | 2 | Note, Eating time, Medication and suppliment, All
2 | Feedogram display and functionality changes | 36 | 6 | As per the provided document"Feedback_20150228"
3 | Feedogram page design with button arrangements | 6 | 2 | As per the provided document"Feedback_20150228"
4 | Filtered feedogram display for water and medicine | 6 | 2 | As per the provided document"Feedback_20150228"
5 | Weekday and Weekend aggregate display changes | 8 | 2 | As per the provided document"Feedback_20150228"
6 | Active timer for last calorie intake | 4 | 1 | As per the provided document"Feedback_20150228"
7 | view chart changes by clicking the history in Feedogram page | 36 | 4 | As per the provided document"Feedback_20150228"
8 | small thumbnail image of the food will pop-up randomly from the feedogram hash marks | 16 | 4
9 | In Feedogram page, display images or food collage as per the selected area for the particular time range | 16 | 4 | To make the paricular area as per the time range per week clickable and Call the API to send image
10 | Set reminder for medication and supplements like alarm | 16 | 2 | As per the understanding, we have completed this functionality on the Web and push notification is going as per the scheduled time. But, now this functionality need to add in the Mobile app and local reminder like alarm
11 | New layout integration | 40 | 8 | After the final layout provided and depends upon the layout
12 | Auto layout | 80 | 20 | After the final layout provided and depends upon the layout
13 | Help | 16 | 2 | Modification after the final layout provided
14 | Display the amount options to set the food taken with each selected tag dynamically to set the amount of food taken | 24 | 4 | After taking the picture & in common food
15 | Send the chosen amount with annotation within the annotation file | 6
16 | Filter food collage location, food, medication etc type wise | 16 | 4
| Total | 338 | 67
| Project Management and Scrum | 61 |  | 15% of Total hour
| Total Hour | 466
Android Development
1 | Push notification On/Off for different feature | 12 | 2 | Note, Eating time, Medication and suppliment, All
2 | Feedogram display and functionality changes | 36 | 6 | As per the provided document"Feedback_20150228"
3 | Feedogram page design with button arrangements | 6 | 2 | As per the provided document"Feedback_20150228"
4 | Filtered feedogram display for water and medicine | 8 | 2 | As per the provided document"Feedback_20150228"
5 | Weekday and Weekend aggregate display changes | 8 | 2 | As per the provided document"Feedback_20150228"
6 | Active timer for last calorie intake | 4 | 1 | As per the provided document"Feedback_20150228"
7 | view chart changes by clicking the history in Feedogram page | 36 | 4 | As per the provided document"Feedback_20150228"
8 | small thumbnail image of the food will pop-up randomly from the feedogram hash marks | 16 | 4
9 | In Feedogram page, display images or food collage as per the selected area for the particular time range | 16 | 4 | To make the paricular area as per the time range per week clickable and Call the API to send image
10 | Set reminder for medication and supplements | 16 | 2 | As per the understanding, we have completed this functionality on the Web and push notification is going as per the scheduled time. But, now this functionality need to add in the Mobile app and local reminder like alarm
11 | New layout integration | 40 | 8 | After the final layout provided and depends upon the layout
12 | Layout adjustment for different screen size | 60 | 20 | After the final layout provided and depends upon the layout
13 | Help | 16 | 2 | Modification after the final layout provided
14 | Display the amount options to set the food taken with each selected tag dynamically to set the amount of food taken | 24 | 4 | After taking the picture & in common food
15 | Send the chosen amount with annotation within the annotation file | 6
16 | Filter food collage location, food, medication etc type wise | 16 | 4
| Total | 320 | 67
| Project Management and Scrum | 58 |  | 15% of Total hour
| Total Hour | 445
API Development
1 | Push notification On/Off for different feature | 8 |  | To update database for Note, Eating time, Medication and suppliment, All
2 | Feedogram API modification to send the data as per the changed layout | 16 |  | Feedogram will be displayed in a weekly aggregate manner for each week. On clicking a weekly data, the feedogram will appear for that week
3 | Feedogram data on filter for All, water and medicine | 12
4 | Aggregate API changes | 6
5 | API for last food intake time | 6
6 | view chart API changes to send the other required information | 12
7 | In Feedogram page, display images or food collage as per the selected area for the particular time range | 16 |  | To send the images to form food Collage for the given time range for that week
8 | Set reminder for medication and supplements | 8 |  | API for synch, add/update
9 | Changes in the API to store the amount of food taken with the annotation | 10
| Total | 94
| Project Management and Scrum | 14 |  | 15% of Total hour
| Total Hour | 108
Web Development
1 | FNDDS calculation logic integration and mapping to participant | 142 | 23 | Implement the logic to calculate the neutrient values using the integrated FNDDS DB
2 | mTurk integration for annotation
3 | Functionality to add/edit the Email body content by the coordinator | 16 | 4
4 | Feedogram layout changes to add box view per day | 16 | 4 | As per the provided document"Feedback_20150228"
5 | Visit question in a new page without login and functionality to save the data | 8 | 2
6 | Display participant's previous research dropout reason if he applied to new research after dropout | 8 | 4
7 | Feedogram mark size changes as per the amout of food chosen | 6 | 2
8 | Implement the logic to auto upgrade participant from Baseline to Intervention and skip the lab visit | 16 | 4
9 | Functionality to upload and display consent on the web | 6 | 1
10 | Functionality to insert Email and full name on the consent | 12 | 2
11 | Generate PDF of the consent with the inserted Email and Full Name | 8 | 2
| Total | 238 | 48
| Project Management and Scrum | 43 |  | 15% of Total hour
| Total Hour | 329

## New_tasks_For_Release
SalkMetabolic Task List not in Clinical Flow document
Sl# | Task | Dev in hrs | QA in hrs | Comments
iOS Development
1 | Water tag in the common food section | 8 | 4
2 | Medication tag in the common food section | 8 | 4
3 | Page to set eating duration target in feedogram with validation | 16 | 2 | Not in clinical flow, but Satchin told us when he has visited our office
4 | Functionality to call API and refresh the feedogram | 8 | 1 | Not in clinical flow, but Satchin told us when he has visited our office
5 | Changes in the view to display the red border as per the target set | 3 | 2 | Not in clinical flow, but Satchin told us when he has visited our office
6 | Feature to add or select medicine annotation like food | 8 | 3
7 | Feature to filter annotation data for medicine, food, beverage and food | 6 | 2
8 | BMI data synchronization | 6 | 2
10 | Location service On/Off functionality | 8 | 2
9 | Filter functionality in BMI for Weekly, Monthly & Yearly | 6 | 2
11 | Filter functionality in Blood Pressure for Weekly, Monthly & Yearly | 6 | 2
12 | Filter functionality in Sleeping time duration for Weekly, Monthly & Yearly | 6 | 2
13 | Filter functionality in Blood Sugar duration for Weekly, Monthly & Yearly | 6 | 2
14 | Prepare new mock up | 8 |  | We created the New design
15 | Integrated New layout | 32 | 8 | Integrated our designed layout
16 | FAQ | 8 | 1
| Total | 143 | 39
| Project Management and Scrum | 27 |  | 15% of Total hour
| Total Hour | 209
Android Development
1 | Water tag in the common food section | 8 | 4
2 | Medication tag in the common food section | 8 | 4
3 | Page to set eating duration target in feedogram with validation | 16 | 2 | Not in clinical flow, but Satchin told us when he has visited our office
4 | Functionality to call API and refresh the feedogram | 8 | 1 | Not in clinical flow, but Satchin told us when he has visited our office
5 | Changes in the view to display the red border as per the target set | 3 | 2 | Not in clinical flow, but Satchin told us when he has visited our office
6 | Feature to add or select medicine annotation like food | 8 | 3
7 | Feature to filter annotation data for medicine, food, beverage and food | 6 | 2
8 | BMI data synchronization | 6 | 2
9 | Location service On/Off functionality | 8 | 2
10 | Filter functionality in BMI for Weekly, Monthly & Yearly | 6 | 2
11 | Filter functionality in Blood Pressure for Weekly, Monthly & Yearly | 6 | 2
12 | Filter functionality in Sleeping time duration for Weekly, Monthly & Yearly | 6 | 2
13 | Filter functionality in Blood Sugar duration for Weekly, Monthly & Yearly | 6 | 2
14 | Prepare new mock up | 8 |  | We created the New design
15 | Integrated New layout | 32 | 8 | Integrated our designed layout
16 | FAQ | 8 | 1
| Total | 143 | 39
| Project Management and Scrum | 27 |  | 15% of Total hour
| Total Hour | 209
API Development
1 | To set the eating duration target in feedogram | 6
2 | API to store BMI data | 4
3 | API to synchronize BMI data | 3
4 | API to store sleeping data | 3
5 | API to store Blood Pressure data | 3
6 | API to store Blood Sugar data | 3
| Total | 22
| Project Management and Scrum | 4 |  | 15% of Total hour
| Total Hour | 26
Web Development
1 | Display eating duration target in feedogram | 4 | 2
2 | Weekly Chart | 6 | 2
3 | Tag cloud display on clicking the weekly chart bar | 8 | 2
4 | Map View and display food taken in info window | 20 | 4
5 | Chart to display Blood Pressure data | 4 | 2
6 | Chart to display Sleep timing data | 4 | 2
7 | Chart to display Blood Sugar data | 4 | 2
8 | Filter functionality in BMI for Weekly, Monthly & Yearly | 3 | 1
9 | Filter functionality in Blood Pressure for Weekly, Monthly & Yearly | 3 | 1
10 | Filter functionality in Sleeping time duration for Weekly, Monthly & Yearly | 3 | 1
11 | Filter functionality in Blood Sugar duration for Weekly, Monthly & Yearly | 3 | 1
| Total | 62 | 20
| Project Management and Scrum | 12 |  | 15% of Total hour
| Total Hour | 94

## Pending_200hrs
SalkMetabolic Pending Task List
Sl# | Task | Dev in hrs | QA in hrs | Comments
iOS Development
1 | New page creation with validation to add Blood Pressure data by participant | 5 | 1 | Other Tools
2 | Feature to call API and also manage local DB to store data | 6 | 1 | Other Tools
3 | Chart to display Blood pressure changes | 5 | 2 | Other Tools
4 | New page creation with validation to add Sleeping time data by participant | 5 | 1 | Other Tools
5 | Feature to call API and also manage local DB to store data | 6 | 1 | Other Tools
6 | Chart to display Sleeping time duration Changes | 5 | 2 | Other Tools
7 | New page creation to add Blood Sugar data by participant | 5 | 1 | Other Tools
8 | Feature to call API and also manage local DB to store data | 6 | 1 | Other Tools
9 | Chart to display Blood Sugar Changes | 5 | 2 | Other Tools
10 | API call Encryption | 8 | 4
11 | Bug fixes | 16 | 2
| Total | 72 | 18
| Total hour | 90
Android Development
1 | New page creation with validation to add Blood Pressure data by participant | 5 | 1 | Other Tools
2 | Feature to call API and also manage local DB to store data | 6 | 1 | Other Tools
3 | Chart to display Blood pressure changes | 5 | 2 | Other Tools
4 | New page creation with validation to add Sleeping time data by participant | 5 | 1 | Other Tools
5 | Feature to call API and also manage local DB to store data | 6 | 1 | Other Tools
6 | Chart to display Sleeping time duration Changes | 5 | 2 | Other Tools
7 | New page creation to add Blood Sugar data by participant | 5 | 1 | Other Tools
8 | Feature to call API and also manage local DB to store data | 6 | 1 | Other Tools
9 | Chart to display Blood Sugar Changes | 5 | 2 | Other Tools
10 | API call Encryption | 8 | 4
11 | Bug fixes | 16 | 2
| Total | 72 | 18
| Total hour | 90
API Development
1 | API call Encryption | 16
2 | API to get the push notification response | 6
| Total | 22
Web Development
2 | Other Fixes | 32 | 8
| Total | 32 | 8
| Total hour | 40

## FNDDS_estimation
SalkMetabolic FNDDS Integration
Sl# | Task | Dev in hrs | QA in hrs | Comments
PDF file go through
1 | PDF file go through | 12
2 | Import data of 14 tables | 6
3 | Create model for 14 tables and adding relationship | 8
4 | View files to insert new data | 24 | 4 | Generating and associate form for different table. Dynamically adding of form to insert multiple number of data.
5 | Save the newly inserted data using Controller | 16 | 2 | Fetching and separating the values for different table and save respectively.
6 | Functionality to search food item by name or food code as in FNDDS | 32 | 6 | Full text search engine. Displaying of data with pagination. Logic to find the measurement description with respect to given food annotation. Displaying the form for measurement.
7 | Integrating calculation logic to find the nutrients | 24 | 8
8 | To save the nutrient result associated with picture or annotation | 16 | 2
9 | Display of calorie intake in participant food log section for each food | 4 | 1
|  | 142 | 23
| Project Management and Scrum | 25 |  | 15% of Total hour
190