## Sheet1
Estimation on SalkMetabolic maintenance work
Sl# | Tasks | Type | Dev hrs | QA hrs | Status | Comments
Web/API Development
1 | In Daily report email, Tomorrow's appointments Count is showing wrong result | BUG | 2 | 1 | CMPL | 2015-07-08
2 | In the dashboard page the counts are not correct | BUG | 3 | 1 | CMPL
3 | While editing research Food intake and water intake fields are coming double times | BUG | 2 | 1 | CMPL
4 | In schedule appointment, there is time zone issue while displaying the time in some scenario | BUG | 2 | 1 | CMPL
5 | Success message is not displaying after some activity | BUG | 3 | 1 | TBD
6 | Intervention started on wrong date, automatically after end of baseline period. If the baseline ended after the set baseline end date | BUG | 1 | 1 | CMPL
7 | Participant-Same name is reflecting in First and last name after registration | BUG | 1 |  | CMPL
8 | Create new research-In Extra questions Food intake and water intake fields are nither reflecting in the investigation report not while sending push notification | BUG | 2 | 2 | CMPL
9 | Edit Research Area:The layout is breaking when we are entering an invalid value for baseline/intervention. | BUG | 1 | 1 | CMPL
10 | Investigation report:The next visit date field should not be included in the investigation report. | BUG | 1 | 1 | CMPL
11 | Create Research:After creation of a particular research no message is displaying about the approval of the research. | BUG | 1 | 1 | CMPL
12 | Research Advertisement:One is able to post his advertisement without entering any banner image. | BUG | 1 | 1 | CMPL
13 | Rejected participant is able to apply for the same research with same email id. | BUG | 3 | 1 | CMPL
14 | Edit participant:There is no validation for weight,height and age field. | BUG | 2 | 1 | CMPL
15 | Rejected participant:When a rejected participant is applying for the same research he is appearing twice in the listing area. | BUG | 2 | 1 | CMPL
16 | In auto generated emails, from address should be depends upon the research study name | ENH | 2 | 1 | CMPL
17 | Question display flow issue in Lab visit research | BUG | 2 | 1 | CMPL
18 | In the emails generated due to action by coordinator, should contain the coordinator's email id | ENH | 2 | 1 | CMPL
19 | In participant list: hide the "email, first name and last name" Add a button to display this information. On clicking that button it will ask for user-name and password. After giving the correct credentials the participant list will be displayed including "email, first name, last name and phone number" | ENH | 7 | 2 | CMPL | 2015-07-15
20 | In downloadable participants excel-sheet, add all the fields displayed in active participant list | ENH | 2 | 1 | CMPL
21 | In participant detail page, remove the email & phone no and replace the name with PID | ENH | 1 | 1 | CMPL
22 | While sign up through the application, display appropriate validation message why s/he is not eligible | ENH | 3 | 1 | CMPL
23 | Display Health records in table view with measured date | ENH | 4 | 1 | CMPL
24 | In advertisement server, second line below the logo in the header section should be dynamic. Coordinator will add the address while creating the research | ENH | 1 | 1 | CMPL
25 | Change the images of salk app with the new mobile launch icon | ENH | 1 |  | CMPL
26 | In Daily report, active and pending for approval participant count will be displayed in sign up section | ENH | 1 | 1 | CMPL
27 | In daily report, change the Other participants section with "waiting for intervention start" | ENH | 1 | 1 | CMPL | Other participant means both who are waiting for intervention and those are completed the intervention still seding data
28 | In Daily report, display count instead of participant list | ENH | 4 | 1 | CMPL
29 | Display report in coordinator side, add pagination to the list of participants | ENH | 6 | 1 | CMPL
30 | Unable to set the intervention date and rename the "My Research" | ENH | 1 | 1 | CMPL
31 | Number of participants enrolled | ENH | 1 |  | CMPL
32 | Number of participant in 6 month follow-up | ENH | 1 |  | CMPL
33 | Number of participant in 1 year follow-up | ENH | 1 |  | CMPL
34 | Number of participants who failed screening | ENH | 1 |  | CMPL
35 | Rename the dropout, rejected and withdrew texts | ENH | 1 |  | CMPL
36 | Number of participants who showed up for the first office visit (screening) | ENH | 1 |  | CMPL
37 | Participants waiting for intervention to start | ENH | 1 |  | CMPL
38 | Number of participants who failed screening or declined to consent | ENH | 1 | 1 | CMPL
39 | Number of participants who consented (this should be “Approved”) | ENH | 1 | 1 | CMPL
40 | In note form, add send now button with confirmation message | ENH | 3 | 1 | CMPL
41 | In advertisement server, Phone related Question changes, validation message changes, consent read information changes and thank you message changes | ENH | 3 | 1 | CMPL
42 | In Feedback section, add archive functionality | ENH | 4 | 1 | CMPL
43 | Only admin can view all the advertisement list on mycircadianclock.org | ENH | 3 | 1 | CMPL
44 | remove water data while calculating feeding duration (Feedogram & feedogram history) | ENH | 2 | 1 | CMPL | 2015-07-23
45 | Appointment set on drag the date form calendar | ENH | 3 | 1 | CMPL
46 | Attach direction image file with the appointment email | ENH | 1 | 1 | CMPL
47 | Display thank you page instead of coordinator signup page, after confirming a appiontment time | ENH | 2 | 1 | CMPL
48 | "Tell us about Yourself" form will be displayed after answering the screening question | ENH | 5 | 1 | CMPL
49 | Display the entered data in "Tell us about yourself" in participant detail page | ENH | 2 | 1 | CMPL
50 | Participant approve email content change | ENH | 1 | 1 | CMPL
51 | Fixed the Audit log page and add menu to the menu list for Admin user | ENH | 1 | 1 | CMPL
52 | Added the access code to the Consent PDF | ENH | 1 |  | CMPL
53 | Adding of final confirmation page for Online study | ENH | 3 | 1 | CMPL
54 | Average sleep time for the week and month while displaying monthly and yearly chart | ENH | 6 | 1 | CMPL | Added monthly and yearly filter on web side
|  | Total | 160
Mobile Development
1 | push notification setting logic change, set default as ON | BUG | 2 | 1 | CMPL | 2015-07-23
2 | After reinstall, store location information while synchronizing food | BUG | 3 | 1 | CMPL
3 | Fix the appointment set issue, after every launch of application the date is set | BUG | 4 | 2 | CMPL
4 | Question page is not working in offline mode, it should not be displayed in offiline | BUG | 2 | 1 | CMPL | We found this issue and hence fixed it
|  | Total | 16
| Research getting updated and move to other coordinator | BUG
| Visit name is not updating while scheduling appointment | BUG